## Annexure I(Descope) (Sch-H) (hidden)
Schedule-H
(See Clauses 10.1.4 and 19.3)
Name of the Project :- |  | Improvement works of Palanpur /Khemana to Aburoad to Swaroopganj Section (from km 601.000 to km 677.000) of NH 27 in the State of Gujarat and Rajasthan on EPC mode
Name of Employer |  | National Highways Infra Project Private Limited
Authority's Engineer |  | M/s L.N Malviya Infra Projects Pvt. Ltd.
Name of EPC Contractor |  | M/s Bhimji Velji Sorathia Construction Private Limited
Contract Price Weightages
Project Cost:- | 380895200 |  |  | Previous Schedule-H |  |  |  | Modified Schedule-H |  |  |  | Cumulative Bill |  | Upto Previous Bill |  | This Bill |  | Remarks | Balance works as per Sch-H |  | Balance Work as Per Site
Item | Weightage in % of CP | Stage for Payment | Percentage weightage | UOM | Scope of work | Rate | Total Amount | UOM | Scope of work | Rate | Total Amount | Quantity | Amount | Quantity | Amount | Quantity | Amount |  | Quantity | Amount | Quantity | Amount
|  | 1.Road Works including Culverts, widening and repair of culverts | 96099858.96
Road Works including Culverts, widening and repair of culverts | 25.23% | C.1- Reconstruction/ New Service Road/ Slip Road (Flexible Pavement)
|  | (1) Earthwork up to top of the sub-grade | 15.99% | km | 6.018 | 2553401.04 | 15366367.4477 | km | 6.018 | 2553401.0382 | 15366367.4477 | 6.018 | 15366367.4477 | 6.018 | 15366367.4477 | 0 | 0 | No Change | 0 | 0
|  | (2) Earthwork in Shoulders | 0.1% | km | 6.018 | 15968.74 | 96099.859 | km | 6.018 | 15968.7369 | 96099.859 | 6.018 | 96099.859 | 6.018 | 96099.859 | 0 | 0 | No Change | 0 | 0
|  | (3) Sub-base Course | 8.85% | km | 6.018 | 1413233.22 | 8504837.518 | km | 6.018 | 1413233.22 | 8504837.518 | 6.018 | 8504837.518 | 6.018 | 8504837.518 | 0 | 0 | No Change | 0 | 0
|  | (4) Non-bituminous Base course | 22.22% | km | 6.018 | 3548253.35 | 21353388.6609 | km | 6.018 | 3548253.3501 | 21353388.6609 | 6.018 | 21353388.6609 | 6.018 | 21353388.6609 | 0 | 0 | No Change | 0 | 0
|  | (5) Bituminous Base course | 26.38% | km | 6.018 | 4212552.81 | 25351142.7936 | km | 6.018 | 4212552.8072 | 25351142.7936 | 5.8775 | 24759279.1242 | 5.8775 | 24759279.1242 | 0 | 0 | No Change | 0.1405 | 591863.6694 | 0.256 | 1078413.5186 | 0.1155
|  | (6) Wearing Coat | 18.07% | km | 6.018 | 2885550.77 | 17365244.5141 | km | 6.018 | 2885550.7667 | 17365244.5141 | 5.4925 | 15848887.5862 | 5.4925 | 15848887.5862 | 0 | 0 | No Change | 0.5255 | 1516356.9279 | 0.5835 | 1683718.8724 | 0.058
|  | D- Reconstruction & New Culverts on existing road, realignments, bypasses | [16 empty] | 0 | 0
|  | Box Culverts | 8.39% | Nos. | 5 | 1612555.63 | 8062778.1667 | Nos. | [9 empty] | Previous schedule-H considered 5 nos. of Box Culverts as per mention in Schedule-B Chainages however the nos. of Box Culverts may reduced due to change in location of service road. Hence, we considering single side of each Box Culvert i.e. 7 Nos. as per schedule-B at present single side 5 nos. | 0 | 0
|  | Super-Structure: On completion of the super-structure (Box Culverts) | [6 empty] | 5 | 977456.4137 | 4887282.0684 | 5 | 4887282.0684 | 5 | 4887282.0684 | 0 | 0 | 89% | 0 | 0
|  | Protection Work : On completion of the Protection Work (Box Culverts) | [6 empty] | 5 | 120809.2197 | 604046.0983 | 4 | 483236.8787 | 4 | 483236.8787 | 0 | 0 | 11% | 1 | 120809.2197 | 1 | 120809.2197
|  |  | 100% | [15 empty] | 0 | 0
|  | Sub Total (1) |  |  |  |  | 96099858.96 |  |  |  | 93528408.96 |  | 91299379.143 | 44.442 | 91299379.143 | 0 | 0 | 1 |  | 2229029.817 |  | 2882941.6107
|  | 2. Minor bridge/Underpasses/ Overpasses | 7617904 | [15 empty] | 0 | 0
Minor bridge/Underpasses/ Overpasses | 2.0% | A.2- New Minor bridges (length >6 m and < 60 m) | [16 empty] | 0 | 0
|  | (1) Foundation: On completion of the foundation work including foundations for wing and return walls, abutments, piers. | 35% | Mtr. | 17.6 | 151492.41 | 2666266.4 | Mtr. | 2 | 1333133.2 | 2666266.4 | 2 | 2666266.4 | 2 | 2666266.4 | 0 | 0 | Scope considering as per Schedule-B in Nos. (LHS-1 & RHS-1 =2 Nos.) | 0 | 0
|  | (2) Sub-structure: On completion of abutments, piers up to the abutment/ pier cap including wing/ return wall up to top | 34.5% | Mtr. | 17.6 | 149328.23 | 2628176.88 | Mtr. | 2 | 1314088.44 | 2628176.88 | 2 | 2628176.88 | 2 | 2628176.88 | 0 | 0 |  | 0 | 0
|  | (3) Super-structure: On completion of the super-structure in all respects including Girder, Deck slab, bearings. | 25% | Mtr. | 17.6 | 108208.86 | 1904476 | Mtr. | 2 | 952238 | 1904476 | 2 | 1904476 | 2 | 1904476 | 0 | 0 |  | 0 | 0
|  | (4) Approaches: On completion of approaches including Retaining walls, stone pitching, protection works complete in all respect, tests on completion in all respect and fit for use. | 5% | Mtr. | 17.6 | 21641.77 | 380895.2 | Mtr. | 2 | 190447.6 | 380895.2 | 2 | 380895.2 | 2 | 380895.2 | 0 | 0 |  | 0 | 0
|  | (6) Other Ancillary Works: On completion of wearing coat, expansion joints, hand rails, crash barriers, road signs & markings, tests on completion in all respect. | 0.5% | Mtr. | 17.6 | 2164.18 | 38089.52 | Mtr. | 2 | 19044.76 | 38089.52 | 2 | 38089.52 | 2 | 38089.52 | 0 | 0 |  | 0 | 0
|  |  | 100% | [15 empty] | 0 | 0
|  | Sub Total (2) |  |  |  |  | 7617904 |  |  |  | 7617904 | 10 | 7617904 | 10 | 7617904 | 0 | 0 | 0 |  | 0 |  | 0
|  | 3.Other Works | 277177437.04 | [15 empty] | 0 | 0
Other Works | 72.77% | (i) Toll Plaza & Toll plaza maintenance | 9.63% | Each | 4 | 6673046.8 | 26692187.187 | Each | 4 | [10 empty] | 0
|  | a) Toilet Block upto slab level (Including Plaster) | [6 empty] | 4 | 1933828.078 | 7735312.3122 | 4 | 7735312.3122 | 4 | 7735312.3122 | 0 | 0 | 60% | 0 | 0
|  | b)Miscellanious Items (Finishing of Toilet & Approaches of Static Weigh Bridge) | [6 empty] | 4 | 1289218.7187 | 5156874.8748 | 4 | 5156874.8748 | 4 | 5156874.8748 | 0 | 0 | 40% | 0 | 0
|  | (ii) Road side drains |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  | 0 |  | 0 | 0
|  | Lined Drain | 12.65% | km | 5.81 | 6034930.43 | 35062945.7856 | km | 5.81 | 6034930.43 | 35062945.7856 | 5.542 | 33445584.4431 | 5.542 | 33445584.4431 | 0 | 0 |  | 0.268 | 1617361.3552 |  |  | Completed Bill Pending
|  | (iii) Road signs, safety Devices, Road Furniture etc. | 0.6% | km | 6.018 | 276348.39 | 1663064.6222 | km | 5.81 | 286241.76 | 1663064.6222 | 5.81 | 1663064.6256 | 5.81 | 1663064.6256 | 0 | 0 |  | 0 | 0
|  | (iv) Road markings & Studs | 1.49% | km | 6.018 | 686265.17 | 4129943.8119 | km | 5.81 | 710833.7 | 4129943.8119 | 5.493 | 3904609.5141 | 5.493 | 3904609.5141 | 0 | 0 |  | 0.317 | 225334.2829 | 0.5835 | 414771.464
|  | (v)W-Beam Crash Barrier | 29.77% | km | 32.65 | 2527280.95 | 82515723.0068 | km | 32.66 | 2526507.13 | 82515723.0068 | 29.434 | 74365210.8644 | 26.786 | 67675019.9842 | 2.648 | 6690190.8802 |  | 3.226 | 8150512.0014 | 3.226 | 8150512.0014
|  | a) Bus Shelter | 3.97% | Each | 8 | 1375493.03 | 11003944.2505 | Each | 8 | 1375493.03 | 11003944.2505 | 8 | 11003944.24 | 8 | 11003944.24 | 0 | 0 |  | 0 | 0
|  | b) Wayside Amenities excluding Slip Roads & but including all internal roads (Service areas including Bus/Truck Lay-Byes) | 2.35% | Each | 2 | 3256834.89 | 6513669.7704 | Each | 2 | 3256834.89 | 6513669.7704 | 2 | 6513669.78 | 2 | 6513669.78 | 0 | 0 |  | 0 | 0
|  | c) Others(Kerbs/Pedestrian Railing) | 7.18% | km |  |  |  | km | 6.56 | 3033740.85 | 19901339.9795 | 6.56 | 19901339.976 | 6.469 | 19625269.5587 | 0.091 | 276070.4173 | Kerb Rising & Railling Providing & Fixing | 0 | 0 |  | 0
|  | i) Kerb Rising |  | km | 11.62 | 856339.93 | 9950669.9897 | km | [10 empty] | 0 | 0 |  | 0
|  | ii) Pedestrian Railing |  | km | 5.81 | 1712679.86 | 9950669.9897 | km | [10 empty] | 0 | 0 |  | 0
|  | (vii) Rain Water Harvesting | 5.69% | Nos. | 10 | 1577139.62 | 15771396.1676 | Nos. | 10 | 1577139.62 | 15771396.1676 | 9 | 14194256.58 | 9 | 14194256.58 | 0 | 0 |  | 1 | 1577139.62 |  | 0 | Completed Bill Pending (Chamber Casting Pending)
|  | (x) Street Lighting | 5.92% | km |  |  |  | km | [7 empty] | 0 | 0 |  | 0 | 0 |  | 0 |  | 150
|  | a) Highway Street Lighting |  | km | 12.03 | 954799.0849 | 11486232.9909 | km | 12.63 | 909440.4585 | 11486232.9909 | 12.63 | 11486232.9909 | 0 | 0 | 12.63 | 11486232.9909 |  | 2.7889e-13 | 2.5363e-07 |  | 0
|  | b) Solar Blinker |  | Nos. | 315 | 15627.5279 | 4922671.2818 | Nos. | 315 | 15627.5279 | 4922671.2818 | 116 | 1812793.2339 | 116 | 1812793.2339 | 0 | 0 |  | 199 | 3109878.0479 | 199 | 3109878.0479
|  | (xvii) Junction Improvement | 16.66% | Each | 27 | 1710287.44 | 46177761.0109 | Each | [10 empty] | 0 | 0 |  | 0
|  | a) Junctions Upto WMM Level | [6 empty] | 28 | 824602.8752 | 23088880.5054 | 27 | 22264277.6302 | 27 | 22264277.6302 | 0 | 0 | 50% | 1 | 824602.8752 | 1 | 824602.8752
|  | b) Junctions DBM Level | [6 empty] | 28 | 296857.0351 | 8311996.982 | 25 | 7421425.8767 | 25 | 7421425.8767 | 0 | 0 | 18% | 3 | 890571.1052 | 3 | 890571.1052
|  | c) Junctions BC Level | [6 empty] | 28 | 296857.0351 | 8311996.982 | 25 | 7421425.8767 | 25 | 7421425.8767 | 0 | 0 | 18% | 3 | 890571.1052 | 3 | 890571.1052
|  | d) Junction Miscellanious Items (Marking & Road Furniture etc. | [6 empty] | 28 | 230888.8051 | 6464886.5415 | 25 | 5772220.1264 | 25 | 5772220.1264 | 0 | 0 | 14% | 3 | 692666.4152 | 3 | 692666.4152
|  | (xviii) Typical Public Charging Station (PCS) | 3.45% | Each | 4 | 2390655.39 | 9562621.5779 | Each | 4 | 2390655.39 | 9562621.5779 | 4 | 9562621.56 | 4 | 9562621.56 | 0 | 0 |  | 0 | 0 |  | 0
|  | (ix) Solar Panel (10 KW Tata Solar Panels) (Area required = 1000 sqft) | 0.64% | Each | 4 | 443483.9 | 1773935.5971 | Each | 4 | 443483.9 | 1773935.5971 | 4 | 1773935.6 | 4 | 1773935.6 | 0 | 0 |  | 0 | 0 |  | 0
|  |  | 100% | [15 empty] | 0 | 0 |  | 0
|  | Sub Total (3) |  |  |  |  | 277177437.04 |  |  |  | 263377437.04 |  | 245398800.1051 |  | 226946305.8166 |  | 18452494.2885 |  |  | 17978636.8082 |  | 14973573.014
| 100% |  | 100% |  |  |  | 380895200 |  |  |  | 364523750 |  | 344316083.2481 |  | 325863588.9596 | 0 | 18452494.2885 |  |  | 20207666.6252 |  | 17856514.6247
0
Authorised Signatory
M/s Bhimji Velji Sorathia
Construction Pvt. Ltd.
Project Manager
NWPPL
Project Manager
NHIPMPL

## Annexure-IIBOQ(actual balance)
NHIT Eastan Project Pvt. Ltd
Annexure C3 - BoQ Improvement works of Palanpur /Khemana to Aburoad to Swaroopganj Section (from km 601.000 to km 677.000) of NH 27 in the State of Gujarat and Rajasthan on EPC mode
S No | Item Description |  | Unit | Rate | Balance Quantity
[5 empty] | Quantity | Amount (Rs.)
1 | Service Road & Junction
1 | Excavation upto the depth of Embankment:Excavation in Soil using Hydraulic Excavator and Tippers with disposal. Scope of Work: Excavation for roadwork in soil using a hydraulic excavator of 0.9 cum bucket capacity, including cutting, trimming of bottom and side slopes, loading into tippers, and transporting the excavated material to the embankment location, within all lifts and lead up to 1000 metres, in accordance with specified lines, grades, and cross-sections. Execution Requirements: 1) Carry out soil excavation using hydraulic excavator (0.9 cum bucket size). 2) Load excavated soil into tippers without spillage. 3) Trim side slopes and bottom in accordance with design drawings. 4) Transport material to designated embankment site within 1000 m. 5) Maintain line, level, and compaction specifications. 6) Follow safety, environmental, and haul route management norms. Rate Inclusions: Includes Labour, machinery (excavator & tippers), fuel, trimming, loading, transport within 1000 m, traffic control, safety compliance, and supervision. Relevant Code / Specifications: MoRTH Clause 301 ( Generalized) | Excavation | Cum |  | 650 | 0
2 | Embankment Construction with Material Obtained from Borrow Pits Identification of Activity: Construction of embankment using approved soil obtained from borrow pits, including excavation, loading, transportation, unloading. Method of Construction: 1) Identify and approve borrow pit sources. 2) Excavate and load earth using hydraulic excavators. 3) Transport material using tippers to the construction site. 4) Spread uniformly using graders and level to required profile. 5) Compact each layer using vibratory rollers. 6) Maintain moisture content by sprinkling water as needed. Rate Inclusions: The quoted rate shall include the cost of all labour, machinery (excavators, tippers, graders, rollers, water tankers), materials, fuel, lead and lift, quality control, water for compaction. Also includes testing and safety compliance. Relevant Code / Specification: MoRTH Specification Clause 305.3 Note: If earth is obtained from government land, compensation shall be excluded. | Embankment | Cum |  | 325 | 0
3 | Construction of Subgrade and Earthen Shoulders Scope of Work: Construction of subgrade and earthen shoulders using approved material obtained from borrow areas, carried to site with all lifts and leads, and laid in layers not exceeding Specific Thickness. The material shall meet the quality parameters defined in MoRTH Clause 305, ensuring proper gradation, moisture, and plasticity. Execution Requirements: 1) Transport approved borrow material to the site and spread in uniform layers. 2) Maintain layer thickness not exceeding specified thickness (shall not be more than 250 mm when vibratory roller/ vibratory soil commpactor is used & shall not be more than 200 mm when 80-100 kN Static roller is used) 3) Compact the subgrade and the earthen shoulders to 97% MDD or above, both as per IS 2720 (Part 8). 4) Ensure proper grading, slope, and level in accordance with approved drawings. 5) Conduct field density and moisture content tests. 6) Perform surface dressing and provide drainage profile for shoulders. 7) Ensure environmental compliance and maintain safe working conditions. Rate Inclusions: The rate shall include cost of all labour, borrow area development, material procurement, loading, unloading, transportation with all lifts and leads, spreading, grading, compaction with mechanical means, surface dressing, quality control testing (MDD, moisture, gradation), and all incidental works required for proper completion as per specifications. Relevant Code : MoRTH Clause 305 | Subgrade | Cum |  | 325 | 0
4 | Construction of Granular Sub-Base (Grade IV Material) Grading IV Material - ( Mix in Place) Scope of Work: Construction of granular sub-base using close graded material conforming to MoRTH Table 400-1, by spreading the approved material in uniform layers over the prepared subgrade, mixing the material in place using a mechanical rotavator at Optimum Moisture Content (OMC), and compacting it with vibratory rollers to achieve the required density. The work shall be executed as per lines, levels, and cross-sections shown in the drawings or as directed by the Engineer.. Method of Construction: 1) Subgrade Preparation: Clear and level the subgrade as per Clause 301/305. Lightly sprinkle with water and compact using a smooth roller. 2) Material Spreading: Spread the approved close graded material in uniform layers (≤200 mm uncompacted) using a motor grader, as per specified alignment and cross-section. 3) In-Place Mixing: Mix the material in place using a mechanical rotavator, adding water as required to achieve OMC. 4) Compaction: Compact using a vibratory roller (80–100 kN) to achieve a minimum of 98% MDD as per IS:2720 (Part 8). Begin rolling from lower edge and proceed to crown. 5) Surface Finish: Ensure the surface is smooth, free from segregation, and conforms to specified lines and grades. Rolling overlap shall be at least 1/3rd width per pass. 6) Testing & Quality Control: Check moisture content before compaction (1–2% below OMC). Conduct field density tests at 50 m intervals or as directed by the Engineer. Note : When the granular sub-base is constructed in two layers each individual layer shall not be less than 150 mm, in accordance with MoRTH Clause 401.2.1. Rate Inclusions: The rate includes the cost of all labour, approved materials, mixing in place using rotavator at OMC, water, spreading, compaction using vibratory roller, transportation , quality control tests, use of all tools, plants, equipment, safety measures and all incidental works to complete the item Relevant Code / Specifications: MoRTH Clause 401 , MoRTH Table 400-1 | GSB | Cum |  | 130 | 0
5 | Construction of Wet Mix Macadam (WMM): Scope of Work: Construction of Wet Mix Macadam using crushed stone aggregates conforming to MoRTH Clause 406, laid by mechanical paver in uniform layers not exceeding 200 mm thickness, mixed with water to achieve optimum moisture content and compacted to required density. Execution Requirements: 1) Source approved aggregates as per project specifications. 2) Prepare the surface by cleaning, leveling, and ensuring cross-slope as per drawings. 3) Mix aggregates with controlled water addition in a mechanical mixer. 4) Lay WMM using a mechanical paver, ensuring proper grade, slope, and layer thickness (Single layer ≤ 200 mm). 5) Compact each layer using an 8–10 tonne vibratory roller to achieve at least 98% of Maximum Dry Density (MDD) per IS 2720 (Part 8). 6) Conduct field density tests every 50 m or as directed by the Engineer. 7) Ensure GPS-enabled paver use with a minimum blade length of 3.05 m for accurate alignment and finish.Rate Inclusions :The rate includes cost of aggregates, water, mixing, laying, rolling, labour, machinery (paver, roller), fuel, surface preparation, compaction, testing, royalty, transportation, and all incidental works. It also includes and environmental and safety measures. Relevant Code / Specifications: MoRTH Clause 406 | WMM | Cum |  | 162.5 | 0
6 | Prime Coat over Granular Base – Using SS1 Grade Bitumen Emulsion Scope of Work: Applying primer coat using SS1 grade bitumen emulsion over prepared stabilized soil base/crusher run macadam, including cleaning and spraying. Execution Requirements: 1) Mechanically clean the compacted surface. 2) Use SS1 bitumen emulsion as per IS:8887. 3) Spray uniformly at 0.90–1.20 kg/sqm using pressure sprayer. 4) Ensure surface is damp, not wet. 5) Allow minimum 24 hours curing; restrict traffic. Rate Inclusions: Bitumen emulsion, surface prep, labour, equipment, spraying, curing, PPE, barricading, and all incidental items. Relevant Code / Specification: MoRTH Clause 502 , IS:8887, Table 500-3 | Prime Coat | Sqm |  | 2348 | 0
7 | Tack Coat on Bituminous Surfaces Scope of Work: Providing and applying tack coat using bitumen emulsion on a prepared bituminous surface to ensure effective bonding with the overlying bituminous layer. Execution Requirements: 1) Clean the bituminous surface using a mechanical broom to remove dust and debris. 2) Use RS-1 grade bitumen emulsion conforming to IS:8887. 3) Apply uniformly at a rate of 0.20 to 0.30 kg/sqm using a bitumen pressure distributor. 4) Maintain spray temperature for Bitumious emulsion around 20°C to 70°C, and for CutBack 50°C to 80°C for best results. 5) Avoid overlapping, streaking, or excess pooling; ensure full surface coverage. Rate Inclusions: Rate includes Bitumen emulsion, labour, cleaning, spraying equipment, fuel, PPE, traffic control, Safety compliance and all incidental works. Relevant Code / Specification: MoRTH Clause 503, IS:8887 | Tack Coat | Sqm |  | 9716 | 0
8 | Dense Bituminous Macadam: Grade 2 VG 40 Scope of Work: Providing and laying Dense Graded Bituminous Macadam (DBM) with 26.5 mm nominal size aggregates (Grading 2) premixed with bituminous binder in a hot mix plant, transported and laid over a prepared surface using sensor-controlled paver finisher, and compacted to achieve the specified grade, density, and finish. Execution Requirements: 1) Use Grading 2 aggregates, VG-40 bitumen @ 4.5%, and filler; mix in approved HMP. 2) Maintain mixing temp: 160–170°C, laying ≥150°C, rolling ≥100°C. 3) Lay mix using sensor-controlled hydrostatic paver finisher to proper profile and level. 4) Maintain layer thickness around 50–75 mm. 4) Compact with smooth wheel, vibratory, and PTR rollers to achieve ≥92% lab density (IS:12091). Rate Inclusions :The rate shall include cost of all materials (VG-40 bitumen, aggregates, mineral filler), mixing in HMP, heating, transportation, laying with paver, compaction using rollers, quality control testing, labour, machinery, fuel, PPE, barricading, signage, traffic control, environmental and safety compliance, and all incidental works required to complete the job in accordance with MoRTH specifications. Relevant Code / Specification: MoRTH Clause 505 | DBM | Cum |  | 182.4 | 0
9 | Bituminous Concrete – Grading 2 (VG-40, 5.4%) Scope of Work: Providing and laying Bituminous Concrete (BC) with Grading II aggregate using higher capacity batch type hot mix plant, premixed with VG-40 bitumen @ 5.4% by weight of total mix and filler, including transportation, laying by hydrostatic sensor paver, and compaction with rollers as per MoRTH Clause 507. Execution Requirements: 1) Prepare mix with VG-40 binder @ 5.4%, Grading 2 aggregates, and filler in HMP. 2) Maintain mix temp 160–170°C, laying temp ≥150°C, rolling temp ≥100°C. 3) Lay mix using sensor paver to desired camber, grade, and level. 4) Compact with smooth, vibratory, and tandem rollers to achieve ≥92% lab density. 5) Maintain layer thickness of 30-40 mm. Rate Inclusions:Covers the complete scope including cost of materials (VG-40, aggregates, filler), HMP operation, transportation, laying, compaction, site preparation, testing, safety, and environmental management. Relevant Specification: MoRTH Clause 507 | BC | Cum |  | 242.72 | 0
|  |  |  | Total Amount:- |  | 0

## Rate Summary (hidden)
Sl No. | Activities | UOM | Basic Rate | Escalation | Final | Remark
1 | Excavation Road | Cum | 91.5 | 0.14094 | 104.3961 | SOR 2022-23 Sl Nos-3.3
2 | Excavation Structure | Cum | 265 | 0.14094 | 302.3492 | SOR 2022-23 Sl Nos-3.13 (A.i) | Price Adjustment
3 | Embankment Borrow Area | Cum | 146.9 | 0.14094 | 167.6042 | SOR 2022-23 Sl Nos-3.16 | S No | Item Description | Indices March 2023 | Indices @ July-2026 | Price Adjustment Factor | Remarks
4 | Subgrade | Cum | 175.5 | 0.14094 | 200.2351 | SOR 2022-23 Sl Nos-3.18
5 | GSB | Cum | 682.69 | 0.14094 | 778.9087 | SOR 2022-23 Sl Nos-4.1 (iv) | 1 | Price Adjustment Factor @ All Commodities- WPI | 151 | 168.3 | 11.46%
6 | WMM | Cum | 822.65 | 0.14094 | 938.5948 | SOR 2022-23 Sl Nos-4.14 (B) | 2 | CPI | 129.4 | 155.6 | 20.25%
7 | Tack Coat | Sqm | 9.1 | 0.14094 | 10.3826 | SOR 2022-23 Sl Nos-5.2 (i) | 3 | Weighted Price Index (70%xWPI + 30%xCPI) |  |  | 14.09%
8 | Prime Coat | Sqm | 26 | 0.14094 | 29.6645 | SOR 2022-23 Sl Nos-5.1(A.i)
9 | DBM Grade-1 | Cum | 6450.6 | 0.14094 | 7359.7512 | SOR 2022-23 Sl Nos-5.4 (i)
10 | BC Grade-1 | Cum | 8170.5 | 0.14094 | 9322.0549 | SOR 2022-23 Sl Nos-5.5(i)
11 | M20 Kerb | RMT | 153 | 0.14094 | 174.5639 | SOR 2022-23 Sl Nos-8.1(ii)
12 | Filter Media | Cum | 579.8 | 0.14094 | 661.5173 | SOR 2022-23 Sl Nos-13.10
13 | PCC M-15 | Cum | 4050 | 0.14094 | 4620.8093 | SOR 2022-23 Sl Nos-9.6 (A.ii)
14 | RCC M-25 | Cum | 5389 | 0.14094 | 6148.5287 | SOR 2022-23 Sl Nos-9.6 (E.ii)
15 | HYSD FE-5000 | MT | 67970 | 0.14094 | 77549.7299 | Meterial Rate +7000 for Cut, bend & Placing
16 | Brick masonry | Cum | 5231.18 | 0.14094 | 5968.4654 | SOR 2022-23 Sl Nos-12.5
17 | Weep Hole | Nos. | 104 | 0.14094 | 118.6578 | SOR 2022-23 Sl Nos-13.8
18 | Stone/Boulder | Cum | 1041 | 0.14094 | 1187.7191 | SOR 2022-23 Sl Nos-16.4 (A)
19 | Sand Filling | Cum | 355.22 | 0.14094 | 405.2849 | SOR 2022-23 Sl Nos-12.3
20 | Median filling | Cum | 189.8 | 0.14094 | 216.5505 | SOR 2022-23 Sl Nos-4.17
21 | Painting Concrete Surface-Road | Sqm | 71 | 0.14094 | 81.0068 | SOR 2022-23 Sl Nos-8.8
22 | Painting Steel Surface | Sqm | 64 | 0.14094 | 73.0202 | SOR 2022-23 Sl Nos-8.9
23 | Road Marking | Sqm | 427 | 0.14094 | 487.1816 | SOR 2022-23 Sl Nos-8.13
24 | "W" metal beam crash barrier | RMT | 3388 | 0.14094 | 3865.5066 | SOR 2022-23 Sl Nos-8.23 (A)
25 | PGR | RMT | 3129 | 0.14094 | 3570.003 | SOR 2022-23 Sl Nos-14.8
26 | Stud | Nos. | 619 | 0.14094 | 706.2422 | SOR 2022-23 Sl Nos-8.35
PRIME COAT
[9 empty] | 3.29 | Prime Coat
[10 empty] | Providing and applying primer coat over prepared surface or granular base with bitumen emulsion SS-1 as per IS: 8887 & manufacturer’s specifications @ 6 kg /10 Sqm with a self propelled or towed bitumen pressure sprayer equipped for spraying the material uniformly at specified rates and temperatures as per MoRTH specification CI 502 & 112 (Including cleaning of road surface ) |  | Sq. m |  |  | 26
[10 empty] | Basic rate for Construction of Prime Coat per Sqm |  |  |  |  | 26
[10 empty] | TOTAL RATE of Construction of Prime Coat per Sqm |  |  |  |  | 26
[10 empty] | Deduct Cost of Emsulsion SS1 as per SOR |  | MT | 0.00065 | 42000 | -27.3
[10 empty] | Add Cost of Emsulsion SS1 as per Current Rate |  | MT | 0.00065 | 66552 | 43.2588
[10 empty] | Final Rate |  |  |  |  | 41.9588

## SR Flexible Pavement
Service Road
Construction of New RD and junction improvement work
S. No | Chainage (km) |  | Side | Length (m) | Width (m) | Milling | BC | DBM | Prime Coat (Sqm) | Tack Coat (Sqm) | DBM | Tack Coat (Sqm) | BC Qty (Cum) | Remarks | Sch _B /Maint. | IE Observation
| From | To
DBM Location
1 | 637700 | 637740 | LHS | 40 | 3.5 |  |  | 0.05 | 140 | 140 | 7 |  | 0 | SRD | Sch _B | 3.5 Mtr width Balance
2 | 637640 | 637720 | RHS | 80 | 3.5 |  |  | 0.05 | 280 | 280 | 14 |  |  | SRD | Sch _B | 3.5 Mtr width Balance
3 | 637540 | 637640 | RHS | 100 | 3.5 |  |  | 0.05 | 350 | 350 | 17.5 |  |  | SRD | Sch _B | 3.5 Mtr width Balance
4 | 647200 | 647305 | LHS | 105 | 2 |  |  | 0.05 | 210 | 210 | 10.5 |  |  | SRD | Sch _B | 2.0 Mtr width Balance
5 | 647350 | 647355 | LHS | 5 | 2 |  |  | 0.05 | 10 | 10 | 0.5 |  |  | SRD | Sch _B | 2.0 Mtr width Balance
6 | 647420 | 647428 | LHS | 8 | 2 |  |  | 0.05 | 16 | 16 | 0.8 |  |  | SRD | Sch _B | 2.0 Mtr width Balance
7 | 647650 | 647668 | LHS | 18 | 2 |  |  | 0.05 | 36 | 36 | 1.8 |  |  | SRD | Sch _B | 2.0 Mtr width Balance
8 | 676661 | 676800 | LHS | 139 | 3.5 |  |  | 0.05 | 486.5 | 486.5 | 24.325 |  |  | SRD | Sch _B | 3.5 Mtr width Balance
9 | 676805 | 676822 | LHS | 17 | 3.5 |  |  | 0.05 | 59.5 | 59.5 | 2.975 |  |  | SRD | Sch _B | 3.5 Mtr width Balance
Entry & Exit
10 | 676945 | 677000 | LHS | 55 | 2 |  |  | 0.05 | 110 | 110 | 5.5 |  |  | SRD | Sch _B | 2.0 Mtr width Balance exit side
BC Location
1 | 647350 | 647355 | LHS | 5 | 2 |  | 0.04 |  |  |  |  | 10 | 0.4 | SRD | Sch _B | 2.0 Mtr width Balance
2 | 647420 | 647428 | LHS | 8 | 2 |  | 0.04 |  |  |  |  | 16 | 0.64 | SRD | Sch _B | 2.0 Mtr width Balance
3 | 647650 | 647668 | LHS | 18 | 2 |  | 0.04 |  |  |  |  | 36 | 1.44 | SRD | Sch _B | 2.0 Mtr width Balance
4 | 676805 | 676822 | LHS | 17 | 3.5 |  | 0.04 |  |  |  |  | 59.5 | 2.38 | SRD | Sch _B | 3.5 Mtr width Balance
5 | 637700 | 638000 | LHS | 300 | 3.5 |  | 0.04 | 0 |  |  | 0 | 1050 | 42 | SRD | Sch _B | 3.5 Mtr width Balance
6 | 637200 | 637720 | RHS | 520 | 3.5 |  | 0.04 | 0 |  |  | 0 | 1820 | 72.8 | SRD | Sch _B | 3.5 Mtr width Balance
7 | 647200 | 647305 | LHS | 105 | 2 |  | 0.04 | 0 |  |  | 0 | 210 | 8.4 | SRD | Sch _B | 2.0 Mtr width Balance
8 | 676661 | 676800 | LHS | 139 | 3.5 |  | 0.04 | 0 |  |  | 0 | 486.5 | 19.46 | SRD | Sch _B | 3.5 Mtr width Balance
9 | 676945 | 677000 | LHS | 55 | 2 |  | 0.04 | 0 |  |  | 0 | 110 | 4.4 | SRD | Sch _B | 2.0 Mtr width Balance exit side
Entry & Exit
10 | 647120 | 647200 | LHS | 80 | 4 |  | 0.04 | 0 |  |  | 0 | 320 | 12.8 | SRD | Sch _B | Entry side flaring balance
Total Qty:- |  |  |  | 1247 |  |  |  |  | 1698 | 1698 | 84.9 | 4118 | 164.72

## Junctions
Current Status of Initial Improvement works as per Schedule B (As on 08.11.2025)
Junction improvement Work
Sr.no. | Description | Km. | Side | Status of IE's Joint site visit | Quantity |  | Observation |  | 650
[5 empty] | Sch-B | Maintenance |  |  | Excavation | Emb | SG | GSB | Prime Coat | WMM | Tack Coat | DBM | BC | Marking
1 | Junction improvement | 647+040 | LHS | Balance at site (ROW issue) | 1 |  | IE/Balance work as per site condition | All Layer Bal. | 650 | 325 | 325 | 130 | 650 | 162.5 | 1300 | 32.5 | 26 | 97.5
2 | Junction improvement | 652+800 | LHS | Balance at site | 1 |  | IE/Balance work as per site condition | DBM & BC | [6 empty] | 1300 | 32.5 | 26 | 97.5
3 | Junction improvement | 652+800 | RHS | Balance at site | 1 |  | IE/Balance work as per site condition | DBM & BC | [6 empty] | 1300 | 32.5 | 26 | 97.5
|  |  |  | Total Nos=> | 3 |  |  |  | 650 | 325 | 325 | 130 | 650 | 162.5 | 3900 | 97.5 | 78 | 292.5 | 0
[9 empty] | 120 | 60
[9 empty] | 201 | 100.5
[9 empty] | 127.5 | 127.5
[9 empty] | 90 | 90
[9 empty] | 118.8 | 59.4

## Line drain (hidden)
Measurment Sheet
Road Side Drain | [8 empty] | Diamension | [5 empty] | Schedule Quantity | [7 empty] | Drain Cover
S.No. | Chainage |  | Side | Length | Quantity |  | Remark | Observation | Wall Height | Wall Thick | Raft Thick | Raft Width | Slab Thick | Slab Width | Excavation | Levelling Course (M-15) | Foundation (M-25) | Wall (M-25) | Slab (M-25) | HYSD Steel | Weep Hole | Back filling | Slab (M-25) | HYSD Steel
| From | To |  |  | Sch-B | Maintenance
Section-1 (601+000 to 646+000) | [8 empty] | Mtr | Mtr | Mtr | Mtr | Mtr | Mtr | Cum | Cum | Cum | Cum | Cum | MT | Nos. | Cum | Cum | MT
1 | 637.15 | 637.155 | RHS | 5 | 5 | 5 |  | Damaged | 0.6 | 0.1 | 0.15 | 1.55 | 0.1 | 1.55 | 8.3125 | 0.875 | 1.1625 | 0.6 | 0.775 | 0.12687 | 5 | 3 | 0.775 | 0.00775
2 | 637.19 | 637.195 | LHS | 5 | 5 | 5 |  | Damaged | 0.6 | 0.1 | 0.15 | 1.55 | 0.1 | 1.55 | 8.3125 | 0.875 | 1.1625 | 0.6 | 0.775 | 0.12687 | 5 | 3 | 0.775 | 0.00775
3 | 637.22 | 637.223 | LHS | 3 | 3 | 3 |  | Damaged | 0.6 | 0.1 | 0.15 | 1.55 | 0.1 | 1.55 | 4.9875 | 0.525 | 0.6975 | 0.36 | 0.465 | 0.076125 | 3 | 1.8 | 0.465 | 0.00465
4 | 637.28 | 637.285 | LHS | 5 | 5 | 5 |  | Damaged | 0.6 | 0.1 | 0.15 | 1.55 | 0.1 | 1.55 | 8.3125 | 0.875 | 1.1625 | 0.6 | 0.775 | 0.12687 | 5 | 3 | 0.775 | 0.00775
5 | 637.3 | 637.31 | RHS | 10 | 10 | 10 |  | Damaged | 0.6 | 0.1 | 0.15 | 1.55 | 0.1 | 1.55 | 16.625 | 1.75 | 2.325 | 1.2 | 1.55 | 0.25375 | 10 | 6 | 1.55 | 0.0155
6 | 637.35 | 637.353 | RHS | 3 | 3 | 3 |  | Damaged | 0.6 | 0.1 | 0.15 | 1.55 | 0.1 | 1.55 | 4.9875 | 0.525 | 0.6975 | 0.36 | 0.465 | 0.076125 | 3 | 1.8 | 0.465 | 0.00465
7 | 637.42 | 637.425 | LHS | 5 | 5 | 5 |  | Damaged | 0.6 | 0.1 | 0.15 | 1.55 | 0.1 | 1.55 | 8.3125 | 0.875 | 1.1625 | 0.6 | 0.775 | 0.12687 | 5 | 3 | 0.775 | 0.00775
8 | 637.45 | 637.453 | LHS | 3 | 3 | 3 |  | Damaged | 0.6 | 0.1 | 0.15 | 1.55 | 0.1 | 1.55 | 4.9875 | 0.525 | 0.6975 | 0.36 | 0.465 | 0.076125 | 3 | 1.8 | 0.465 | 0.00465
9 | 637.47 | 637.473 | LHS | 3 | 3 | 3 |  | Damaged | 0.6 | 0.1 | 0.15 | 1.55 | 0.1 | 1.55 | 4.9875 | 0.525 | 0.6975 | 0.36 | 0.465 | 0.076125 | 3 | 1.8 | 0.465 | 0.00465
10 | 637.625 | 637.635 | LHS | 10 | 10 | 10 |  | Damaged | 0.6 | 0.1 | 0.15 | 1.55 | 0.1 | 1.55 | 16.625 | 1.75 | 2.325 | 1.2 | 1.55 | 0.25375 | 10 | 6 | 1.55 | 0.0155
11 | 637.65 | 637.66 | LHS | 10 | 10 | 10 |  | Damaged | 0.6 | 0.1 | 0.15 | 1.55 | 0.1 | 1.55 | 16.625 | 1.75 | 2.325 | 1.2 | 1.55 | 0.25375 | 10 | 6 | 1.55 | 0.0155
12 | 637.71 | 637.73 | LHS | 20 | 20 | 20 |  | Damaged | 0.6 | 0.1 | 0.15 | 1.55 | 0.1 | 1.55 | 33.25 | 3.5 | 4.65 | 2.4 | 3.1 | 0.5075 | 20 | 12 | 3.1 | 0.031
13 | 637.74 | 637.745 | LHS | 5 | 5 | 5 |  | Damaged | 0.6 | 0.1 | 0.15 | 1.55 | 0.1 | 1.55 | 8.3125 | 0.875 | 1.1625 | 0.6 | 0.775 | 0.12687 | 5 | 3 | 0.775 | 0.00775
14 | 637.9 | 637.92 | LHS | 20 | 20 | 20 |  | Damaged | 0.6 | 0.1 | 0.15 | 1.55 | 0.1 | 1.55 | 33.25 | 3.5 | 4.65 | 2.4 | 3.1 | 0.5075 | 20 | 12 | 3.1 | 0.031
Total (A) |  |  |  | 107 | 107 | 107 | [18 empty] | Weep Hole | 1 | #REF! |  |  | #REF! | #REF! | Nos
Section-2 (646+000 to 677+000) | [24 empty] | Parapet Wall | 1 | #REF! | #REF! | 0.6 | #REF! | #REF! | Cum
1 | 647.65 | 647.653 | LHS | 3 | 3 | 3 |  | Damaged | 0.9604 | 0.1 | 0.15 | 1.55 | 0.1 | 1.55 | 6.8796 | 0.525 | 0.6975 | 0.57624 | 0.465 | 0.086937 | 3 | 2.8812 | 0.465 | 0.00465
2 | 648.8 | 648.812 | RHS | 12 | 12 | 12 |  | Damaged | 0.9604 | 0.1 | 0.15 | 1.55 | 0.1 | 1.55 | 27.5184 | 2.1 | 2.79 | 2.305 | 1.86 | 0.34775 | 12 | 11.5248 | 1.86 | 0.0186
3 | 660.68 | 660.683 | RHS | 3 | 3 | 3 |  | Damaged | 0.9604 | 0.1 | 0.15 | 1.55 | 0.1 | 1.55 | 6.8796 | 0.525 | 0.6975 | 0.57624 | 0.465 | 0.086937 | 3 | 2.8812 | 0.465 | 0.00465
4 | 666.63 | 666.635 | LHS | 5 | 5 | 5 |  | Damaged | 0.9604 | 0.1 | 0.15 | 1.55 | 0.1 | 1.55 | 11.466 | 0.875 | 1.1625 | 0.9604 | 0.775 | 0.14489 | 5 | 4.802 | 0.775 | 0.00775
5 | 666.83 | 666.845 | LHS | 15 | 15 | 15 |  | Damaged | 0.9604 | 0.1 | 0.15 | 1.55 | 0.1 | 1.55 | 34.398 | 2.625 | 3.4875 | 2.8812 | 2.325 | 0.43468 | 15 | 14.406 | 2.325 | 0.02325
6 | 671 | 671.01 | LHS | 10 | 10 | 10 |  | Damaged | 0.9604 | 0.1 | 0.15 | 1.55 | 0.1 | 1.55 | 22.932 | 1.75 | 2.325 | 1.9208 | 1.55 | 0.28979 | 10 | 9.604 | 1.55 | 0.0155
7 | 676.58 | 676.61 | LHS | 30 | 30 | 30 |  | Damaged | 0.9604 | 0.1 | 0.15 | 1.55 | 0.1 | 1.55 | 68.796 | 5.25 | 6.975 | 5.7624 | 4.65 | 0.86937 | 30 | 28.812 | 4.65 | 0.0465
8 | 676.61 | 676.613 | RHS | 3 | 3 | 3 |  | Damaged | 0.9604 | 0.1 | 0.15 | 1.55 | 0.1 | 1.55 | 6.8796 | 0.525 | 0.6975 | 0.57624 | 0.465 | 0.086937 | 3 | 2.8812 | 0.465 | 0.00465
9 | 676.7 | 676.705 | LHS | 5 | 5 | 5 |  | Damaged | 0.9604 | 0.1 | 0.15 | 1.55 | 0.1 | 1.55 | 11.466 | 0.875 | 1.1625 | 0.9604 | 0.775 | 0.14489 | 5 | 4.802 | 0.775 | 0.00775
10 | 676.85 | 676.855 | RHS | 5 | 5 | 5 |  | Damaged | 0.9604 | 0.1 | 0.15 | 1.55 | 0.1 | 1.55 | 11.466 | 0.875 | 1.1625 | 0.9604 | 0.775 | 0.14489 | 5 | 4.802 | 0.775 | 0.00775
Total (B) |  |  |  | 91 | 91 | 91 |  |  | 0.9604 | 0.1 | 0.15 | 1.55 | 0.1 | 1.55 | 208.6812 | 15.925 | 21.1575 | 17.4793 | 14.105 | 2.6371 | 91 | 87.3964 | 14.105 | 0.14105
Total Balance Qty. (A+B) |  |  |  | 198 | 198 | 198 |  |  | 10.5644 | 1.1 | 1.65 | 17.05 | 1.1 | 17.05 | 595.2499 | 31.85 | 42.315 | 34.9586 | 28.21 | 5.2742 | 182 | 174.7928 | 28.21 | 0.2821
Authorised Signatory
M/s Bhimji Velji Sorathia
Construction Pvt. Ltd.
Project Manager
NHIPMPL

## Road marking (hidden)
Service Road
Road marking
S. No | Chainage (km) |  | Side | Length (m) | EL | CL | Quantity (Sq.M) |  | Observation
| From | To |  |  |  |  | Sch-B | Maintenance
1 | 647350 | 647355 | LHS | 5 | 0.15 | 0.1 | 0.91667 |  | Balance work as per site condition
2 | 647420 | 647428 | LHS | 8 | 0.15 | 0.1 | 1.4667 |  | Balance work as per site condition
3 | 647650 | 647668 | LHS | 18 | 0.15 | 0.1 | 3.3 |  | Balance work as per site condition
4 | 676805 | 676822 | LHS | 17 | 0.15 | 0.1 | 3.1167 |  | Balance work as per site condition
5 | 637700 | 638000 | LHS | 300 | 0.15 | 0.1 | 55 |  | Balance work as per site condition
6 | 637200 | 637720 | RHS | 520 | 0.15 | 0.1 | 95.3333 |  | Balance work as per site condition
7 | 647200 | 647305 | LHS | 105 | 0.15 | 0.1 | 19.25 |  | Balance work as per site condition
8 | 676661 | 676800 | LHS | 139 | 0.15 | 0.1 | 25.4833 |  | Balance work as per site condition
9 | 676945 | 677000 | LHS | 55 | 0.15 | 0.1 | 10.0833 |  | Balance work as per site condition
Entry & Exit
9 | 647120 | 647200 | LHS | 80 | 0.15 | 0.1 | 14.6667 |  | Balance work as per site condition
Total Qty:- |  |  |  | 1247 |  |  | 228.6167
583.5

## Stud (hidden)
Measurment Sheet
Road Studs
SL No | Chainage |  | Side | Length | Quantity (Nos) |  | Description
| From | To |  |  | Sch-B | Maintenance
Section-2 (646+000 to 677+000)
1 | 647350 | 647355 | LHS | 5 | 2 | 2
2 | 647420 | 647428 | LHS | 8 | 2 | 2
3 | 647650 | 647668 | LHS | 18 | 4 | 4
4 | 676805 | 676822 | LHS | 17 | 4 | 4
5 | 637700 | 638000 | LHS | 300 | 66 | 66
6 | 637200 | 637720 | RHS | 520 | 116 | 116
7 | 647200 | 647305 | LHS | 105 | 24 | 24
8 | 676661 | 676800 | LHS | 139 | 30 | 30
9 | 676945 | 677000 | LHS | 55 | 12 | 12
| 647120 | 647200 | LHS | 80 | 18 | 18
Total (B) |  |  |  | 1247 | 278 | 278
Total Balance Qty. (A+B) |  |  |  | 1247 | 278 | 278

## BOX culvert, painting (hidden)
BOX culvert head wall painting
S. No | Item Description | Chainage (km) |  | Side | Nos. | Length (m) | Hight (m) | Painting Quantity (Sqm) |  | Pretection Work Quantity |  | Observation
|  | From | To |  |  |  |  | Sch-B | Maintenance | Sch-B | Maintenance
3 | BOX culvert | 637+715 |  | LHS | 1 | 8.38 | 0.7 | 5.866 |  | 1 |  | IE/Balance work as per site condition (Protection and Painting Bal) | As per Letter Culvert Bal.at Site
[8 empty] | 5.866 |  | 1
S No | Item | Unit | Nos | Length | Width | Thick | Quantity | Sub Total | Rate | Amount
1 | Excavation for Wing Wall | Cum | 2 | 5.635 | 0.75 | 3.95 | 33.3874 | 98.8498 | 302.3492 | 29887.1476
2 | Excavation for Curtain Wall | Cum | 1 | 9.8 | 2.35 | 2.5 | 57.575
3 | Excavation for Rigid Appron | Cum | 1 | 6.15 | 2.85 | 0.45 | 7.8874
2 | PCC for Wing Wall M15 | Cum | 2 | 5.635 | 0.55 | 0.15 |  | 24.3851 | 4620.8093 | 112679.0117
2 | PCC for Curtain Wall M15 | Cum | 1 | 9.8 | 2.15 | 0.15 | 3.1605
| PCC for Curtain Wall M15 (Sub Str) | Cum | 1 | 9.8 | Area= | 1.8975 | 18.5955 |  |  |  | 0.75
| PCC for Rigid Appron M15 | Cum | 1 | 6.15 | 2.85 | 0.15 | 2.6291
3 | Sub-Str Qty M25 | Cum | 2 | 5.635 | 0.25 | 2 |  | 0 | 6148.5287 | 0
|  | Cum | 2 | 1 | 0.25 | 0.3 |  |  |  |  | 4.635 | 21.4832
|  | Cum | 2 | 5.635 | 0.25 | 1.075 |  |  |  |  | 2.85 | 8.1225
4 | Steel HYSD | MT | 100 Kg per Cum |  |  |  | 0 | 0 | 77549.7299 | 0 |  | 13.3607
5 | Boulder for Rigid appron | Cum | 1 | 6.15 | 2.85 | 0.3 | 5.2582 | 5.2582 | 1187.7191 | 6245.3241 |  | 3.6552
5 | Boulder for Flexible appron | Cum | 1 | 9.8 | 6 | 1 | 58.8 | 58.8 | 1187.7191 | 69837.8845
218649.3679

## MBCB (hidden)
(v)W-Beam Crash Barrier
SL No | Chainage |  | Side | Length | Description
| From | To
1 | 668.55 | 669 | LHS | 0.45 | P&F Metal Beam Crash Barrier
2 | 669.08 | 669.3 | LHS | 0.22 | P&F Metal Beam Crash Barrier
3 | 666.95 | 667 | RHS | 0.05 | P&F Metal Beam Crash Barrier
4 | 667.01 | 667.85 | RHS | 0.84 | P&F Metal Beam Crash Barrier
5 | 662.4 | 662.7 | RHS | 0.3 | P&F Metal Beam Crash Barrier
6 | 661.5 | 661.55 | RHS | 0.05 | P&F Metal Beam Crash Barrier
7 | 660.9 | 661 | LHS | 0.1 | P&F Metal Beam Crash Barrier
8 | 660.35 | 660.45 | LHS | 0.1 | P&F Metal Beam Crash Barrier
9 | 660.164 | 660.2 | LHS | 0.036 | P&F Metal Beam Crash Barrier
10 | 658.8 | 658.9 | LHS | 0.1 | P&F Metal Beam Crash Barrier
11 | 657.4 | 657.5 | LHS | 0.1 | P&F Metal Beam Crash Barrier
12 | 657.2 | 657.6 | RHS | 0.4 | P&F Metal Beam Crash Barrier
13 | 654.1 | 654.204 | LHS | 0.104 | P&F Metal Beam Crash Barrier
14 | 651.6 | 651.94 | LHS | 0.34 | P&F Metal Beam Crash Barrier
15 | 651.95 | 652.1 | LHS | 0.15 | P&F Metal Beam Crash Barrier
16 | 651.6 | 651.94 | RHS | 0.34 | P&F Metal Beam Crash Barrier
17 | 651.95 | 652.004 | RHS | 0.054 | P&F Metal Beam Crash Barrier
18 | 651.2 | 651.45 | LHS | 0.25 | P&F Metal Beam Crash Barrier
19 | 651.2 | 651.45 | RHS | 0.25 | P&F Metal Beam Crash Barrier
20 | 649.8 | 650.048 | LHS | 0.248 | P&F Metal Beam Crash Barrier
21 | 639.8 | 640.1 | RHS | 0.3 | P&F Metal Beam Crash Barrier
22 | 638.4 | 638.7 | RHS | 0.3 | P&F Metal Beam Crash Barrier
23 | 638.25 | 638.42 | LHS | 0.17 | P&F Metal Beam Crash Barrier
24 | 634.3 | 634.42 | LHS | 0.12 | P&F Metal Beam Crash Barrier
25 | 634.3 | 634.4 | RHS | 0.1 | P&F Metal Beam Crash Barrier
26 | 628.7 | 629.35 | RHS | 0.65 | P&F Metal Beam Crash Barrier
27 | 628.3 | 628.4 | RHS | 0.1 | P&F Metal Beam Crash Barrier
28 | 627.9 | 628.224 | LHS | 0.324 | P&F Metal Beam Crash Barrier
29 | 628.234 | 628.42 | LHS | 0.186 | P&F Metal Beam Crash Barrier
30 | 627.55 | 627.65 | RHS | 0.1 | P&F Metal Beam Crash Barrier
31 | 626.9 | 627.05 | LHS | 0.15 | P&F Metal Beam Crash Barrier
32 | 626.3 | 626.304 | RHS | 0.004 | P&F Metal Beam Crash Barrier
33 | 626.314 | 626.6 | RHS | 0.286 | P&F Metal Beam Crash Barrier
34 | 626.1 | 626.2 | LHS | 0.1 | P&F Metal Beam Crash Barrier
35 | 623.9 | 623.95 | RHS | 0.05 | P&F Metal Beam Crash Barrier
36 | 622 | 622.2 | LHS | 0.2 | P&F Metal Beam Crash Barrier
37 | 622 | 622.2 | RHS | 0.2 | P&F Metal Beam Crash Barrier
38 | 621.8 | 621.85 | RHS | 0.05 | P&F Metal Beam Crash Barrier
39 | 621.854 | 621.96 | RHS | 0.106 | P&F Metal Beam Crash Barrier
40 | 621.964 | 622 | RHS | 0.036 | P&F Metal Beam Crash Barrier
41 | 621.63 | 621.75 | LHS | 0.12 | P&F Metal Beam Crash Barrier
42 | 621 | 621.02 | RHS | 0.02 | P&F Metal Beam Crash Barrier
43 | 621.03 | 621.1 | RHS | 0.07 | P&F Metal Beam Crash Barrier
44 | 620.8 | 620.89 | RHS | 0.09 | P&F Metal Beam Crash Barrier
45 | 620.8 | 620.9 | LHS | 0.1 | P&F Metal Beam Crash Barrier
46 | 619.6 | 619.65 | LHS | 0.05 | P&F Metal Beam Crash Barrier
47 | 619.5 | 619.7 | RHS | 0.2 | P&F Metal Beam Crash Barrier
48 | 619.05 | 619.4 | RHS | 0.35 | P&F Metal Beam Crash Barrier
49 | 619 | 619.326 | LHS | 0.326 | P&F Metal Beam Crash Barrier
50 | 619.332 | 619.356 | LHS | 0.024 | P&F Metal Beam Crash Barrier
51 | 619.364 | 619.4 | LHS | 0.036 | P&F Metal Beam Crash Barrier
52 | 618.55 | 618.618 | RHS | 0.068 | P&F Metal Beam Crash Barrier
53 | 618.624 | 618.7 | RHS | 0.076 | P&F Metal Beam Crash Barrier
54 | 618.48 | 618.53 | LHS | 0.05 | P&F Metal Beam Crash Barrier
55 | 618 | 618.2 | LHS | 0.2 | P&F Metal Beam Crash Barrier
56 | 617.845 | 617.913 | LHS | 0.068 | P&F Metal Beam Crash Barrier
57 | 617.8 | 617.828 | RHS | 0.028 | P&F Metal Beam Crash Barrier
58 | 617.924 | 618.078 | RHS | 0.154 | P&F Metal Beam Crash Barrier
59 | 616.6 | 616.65 | RHS | 0.05 | P&F Metal Beam Crash Barrier
60 | 615.6 | 615.8 | RHS | 0.2 | P&F Metal Beam Crash Barrier
61 | 615.25 | 615.35 | LHS | 0.1 | P&F Metal Beam Crash Barrier
62 | 615.358 | 615.7 | LHS | 0.342 | P&F Metal Beam Crash Barrier
63 | 615.18 | 615.23 | RHS | 0.05 | P&F Metal Beam Crash Barrier
64 | 614.45 | 614.5 | RHS | 0.05 | P&F Metal Beam Crash Barrier
65 | 613.98 | 614.45 | LHS | 0.47 | P&F Metal Beam Crash Barrier
66 | 613.6 | 613.796 | LHS | 0.196 | P&F Metal Beam Crash Barrier
67 | 613.6 | 613.7 | RHS | 0.1 | P&F Metal Beam Crash Barrier
68 | 612.5 | 612.7 | LHS | 0.2 | P&F Metal Beam Crash Barrier
69 | 611.2 | 611.35 | RHS | 0.15 | P&F Metal Beam Crash Barrier
70 | 611.18 | 611.3 | LHS | 0.12 | P&F Metal Beam Crash Barrier
71 | 610 | 610.1 | LHS | 0.1 | P&F Metal Beam Crash Barrier
72 | 607.4 | 607.5 | LHS | 0.1 | P&F Metal Beam Crash Barrier
73 | 607.2 | 607.3 | RHS | 0.1 | P&F Metal Beam Crash Barrier
74 | 607.2 | 607.3 | LHS | 0.1 | P&F Metal Beam Crash Barrier
75 | 667.6 | 667.8 | LHS | 0.2 | P&F Metal Beam Crash Barrier
76 | 665.3 | 665.516 | RHS | 0.216 | P&F Metal Beam Crash Barrier
77 | 665.523 | 665.6 | RHS | 0.077 | P&F Metal Beam Crash Barrier
78 | 665.3 | 665.516 | LHS | 0.216 | P&F Metal Beam Crash Barrier
79 | 665.523 | 665.6 | LHS | 0.077 | P&F Metal Beam Crash Barrier
80 | 655.35 | 655.514 | RHS | 0.164 | P&F Metal Beam Crash Barrier
81 | 640.15 | 640.25 | RHS | 0.1 | P&F Metal Beam Crash Barrier
82 | 638.5 | 638.9 | Median | 0.4 | P&F Metal Beam Crash Barrier
83 | 635.572 | 635.6 | LHS | 0.028 | P&F Metal Beam Crash Barrier
84 | 635.5 | 635.56 | LHS | 0.06 | P&F Metal Beam Crash Barrier
85 | 632.7 | 632.948 | Median | 0.248 | P&F Metal Beam Crash Barrier
86 | 632.7 | 632.9 | LHS | 0.2 | P&F Metal Beam Crash Barrier
87 | 632.1 | 632.2 | LHS | 0.1 | P&F Metal Beam Crash Barrier
88 | 631.5 | 631.716 | Median | 0.216 | P&F Metal Beam Crash Barrier
89 | 626.9 | 627.1 | Median | 0.2 | P&F Metal Beam Crash Barrier
90 | 623.2 | 623.348 | Median | 0.148 | P&F Metal Beam Crash Barrier
91 | 622.4 | 622.5 | Median | 0.1 | P&F Metal Beam Crash Barrier
92 | 619.79 | 620.298 | Median | 0.508 | P&F Metal Beam Crash Barrier
93 | 619.5 | 619.7 | Median | 0.2 | P&F Metal Beam Crash Barrier
94 | 616.2 | 616.7 | Median | 0.5 | P&F Metal Beam Crash Barrier
95 | 615.8 | 616 | Median | 0.2 | P&F Metal Beam Crash Barrier
96 | 613.95 | 614.35 | Median | 0.4 | P&F Metal Beam Crash Barrier
97 | 604.924 | 605.016 | RHS | 0.092 | P&F Metal Beam Crash Barrier
98 | 604.768 | 604.904 | RHS | 0.136 | P&F Metal Beam Crash Barrier
99 | 604.56 | 604.756 | RHS | 0.196 | P&F Metal Beam Crash Barrier
100 | 604.5 | 604.6 | Median | 0.1 | P&F Metal Beam Crash Barrier
101 | 604.1 | 604.208 | Median | 0.108 | P&F Metal Beam Crash Barrier
102 | 604 | 604.208 | RHS | 0.208 | P&F Metal Beam Crash Barrier
103 | 669.08 | 669.6 | Median | 0.52 | P&F Metal Beam Crash Barrier
104 | 668.55 | 669.08 | Median | 0.53 | P&F Metal Beam Crash Barrier
105 | 668.04 | 668.2 | Median | 0.16 | P&F Metal Beam Crash Barrier
106 | 667.6 | 668.04 | Median | 0.44 | P&F Metal Beam Crash Barrier
107 | 666.8 | 667.05 | Median | 0.25 | P&F Metal Beam Crash Barrier
108 | 665.3 | 665.6 | Median | 0.3 | P&F Metal Beam Crash Barrier
109 | 664.25 | 664.6 | Median | 0.35 | P&F Metal Beam Crash Barrier
110 | 660.2 | 660.5 | Median | 0.3 | P&F Metal Beam Crash Barrier
111 | 659.6 | 659.75 | Median | 0.15 | P&F Metal Beam Crash Barrier
112 | 658.8 | 659.1 | LHS-SR | 0.3 | P&F Metal Beam Crash Barrier
113 | 649.1 | 649.3 | Median | 0.2 | P&F Metal Beam Crash Barrier
114 | 647.85 | 648 | Median | 0.15 | P&F Metal Beam Crash Barrier
115 | 647.6 | 647.75 | Median | 0.15 | P&F Metal Beam Crash Barrier
116 | 621.6 | 621.7 | LHS | 0.1 | P&F Metal Beam Crash Barrier
117 | 621.6 | 621.7 | RHS | 0.1 | P&F Metal Beam Crash Barrier
118 | 612.95 | 613.05 | Median | 0.1 | P&F Metal Beam Crash Barrier
119 | 612.7 | 612.85 | Median | 0.15 | P&F Metal Beam Crash Barrier
120 | 609.6 | 610.1 | Median | 0.5 | P&F Metal Beam Crash Barrier
121 | 608.98 | 609.4 | Median | 0.42 | P&F Metal Beam Crash Barrier
122 | 608.44 | 608.98 | Median | 0.54 | P&F Metal Beam Crash Barrier
123 | 608 | 608.44 | Median | 0.44 | P&F Metal Beam Crash Barrier
124 | 601.65 | 601.798 | Median | 0.148 | P&F Metal Beam Crash Barrier
125 | 601.798 | 602.298 | Median | 0.5 | P&F Metal Beam Crash Barrier
126 | 602.45 | 602.65 | LHS | 0.2 | P&F Metal Beam Crash Barrier
127 | 602.85 | 602.88 | RHS | 0.03 | P&F Metal Beam Crash Barrier
128 | 602.909 | 602.929 | RHS | 0.02 | P&F Metal Beam Crash Barrier
129 | 602.936 | 602.966 | RHS | 0.03 | P&F Metal Beam Crash Barrier
130 | 603.95 | 604 | RHS | 0.05 | P&F Metal Beam Crash Barrier
131 | 604.208 | 604.5 | Median | 0.292 | P&F Metal Beam Crash Barrier
132 | 604.55 | 604.56 | RHS | 0.01 | P&F Metal Beam Crash Barrier
133 | 604.6 | 604.8 | Median | 0.2 | P&F Metal Beam Crash Barrier
134 | 604.756 | 604.768 | RHS | 0.012 | P&F Metal Beam Crash Barrier
135 | 605.016 | 605.1 | RHS | 0.084 | P&F Metal Beam Crash Barrier
136 | 605.5 | 606.25 | Median | 0.75 | P&F Metal Beam Crash Barrier
137 | 605.5 | 605.65 | RHS | 0.15 | P&F Metal Beam Crash Barrier
138 | 605.506 | 605.55 | Median | 0.044 | P&F Metal Beam Crash Barrier
139 | 606.8 | 607 | Median | 0.2 | P&F Metal Beam Crash Barrier
140 | 606.8 | 606.85 | RHS | 0.05 | P&F Metal Beam Crash Barrier
141 | 607.65 | 607.75 | BHS | 0.2 | P&F Metal Beam Crash Barrier
142 | 607.75 | 607.774 | Median | 0.024 | P&F Metal Beam Crash Barrier
143 | 607.75 | 607.882 | Median | 0.132 | P&F Metal Beam Crash Barrier
144 | 613.05 | 613.15 | Median | 0.1 | P&F Metal Beam Crash Barrier
145 | 614.2 | 614.4 | Median | 0.2 | P&F Metal Beam Crash Barrier
146 | 619.7 | 619.79 | Median | 0.09 | P&F Metal Beam Crash Barrier
147 | 623.348 | 623.35 | Median | 0.002 | P&F Metal Beam Crash Barrier
148 | 631.716 | 631.75 | Median | 0.034 | P&F Metal Beam Crash Barrier
149 | 632.7 | 632.8 | RHS | 0.1 | P&F Metal Beam Crash Barrier
150 | 632.948 | 633 | Median | 0.052 | P&F Metal Beam Crash Barrier
151 | 635.56 | 635.572 | LHS-SR | 0.012 | P&F Metal Beam Crash Barrier
152 | 639.21 | 639.22 | RHS | 0.01 | P&F Metal Beam Crash Barrier
153 | 646.4 | 646.45 | RHS | 0.05 | P&F Metal Beam Crash Barrier
154 | 655.35 | 655.414 | LHS | 0.064 | P&F Metal Beam Crash Barrier
155 | 655.424 | 655.47 | LHS | 0.046 | P&F Metal Beam Crash Barrier
156 | 655.514 | 655.55 | RHS | 0.036 | P&F Metal Beam Crash Barrier
157 | 661.2 | 661.264 | LHS | 0.064 | P&F Metal Beam Crash Barrier
158 | 664.27 | 664.52 | LHS | 0.25 | P&F Metal Beam Crash Barrier
159 | 664.55 | 664.65 | Median | 0.1 | P&F Metal Beam Crash Barrier
160 | 664.9 | 665.05 | RHS | 0.15 | P&F Metal Beam Crash Barrier
161 | 666.4 | 666.65 | RHS | 0.25 | P&F Metal Beam Crash Barrier
162 | 668.2 | 668.35 | Median | 0.15 | P&F Metal Beam Crash Barrier
163 | 669.002 | 669.08 | LHS | 0.078 | P&F Metal Beam Crash Barrier
164 | 670.25 | 670.4 | LHS | 0.15 | P&F Metal Beam Crash Barrier
165 | 670.552 | 670.6 | RHS | 0.048 | P&F Metal Beam Crash Barrier
166 | 670.56 | 670.6 | LHS | 0.04 | P&F Metal Beam Crash Barrier
167 | 672 | 672.2 | Median | 0.2 | P&F Metal Beam Crash Barrier
168 | 676.75 | 677 | LHS Median | 0.25 | P&F Metal Beam Crash Barrier
169 | 676.8 | 676.9 | RHS Median | 0.1 | P&F Metal Beam Crash Barrier
170 | 621.63 | 621.7 | LHS | -0.07 | P&F Metal Beam Crash Barrier
171 | 605.506 | 605.55 | Median | -0.044 | P&F Metal Beam Crash Barrier
172 | 607.75 | 607.774 | Median | -0.024 | P&F Metal Beam Crash Barrier
173 | 614.2 | 614.35 | Median | -0.15 | P&F Metal Beam Crash Barrier
174 | 664.55 | 664.6 | Median | -0.05 | P&F Metal Beam Crash Barrier
29.434
|  | Total scope | 32.66
|  | Work done at Site | 29.434
|  | Bal. | 3.226

## PGR (hidden)
PGR
Sr. No. | Chainage |  | Length | Location | Side | Remarks
| From | To
1 | 636.9 | 636.904 | 4 | S/R | LHS
2 | 647.2 | 647.203 | 3 | S/R | LHS
3 | 666.55 | 666.58 | 30 | S/R | LHS
4 | 666.68 | 666.686 | 6 | S/R | LHS
5 | 674 | 674.006 | 6 | S/R | LHS
6 | 674.05 | 674.06 | 10 | S/R | LHS
7 | 676.75 | 676.759 | 9 | S/R | LHS
8 | 676.82 | 676.829 | 9 | S/R | LHS
9 | 671.1 | 671.103 | 3 | S/R | RHS
10 | 648.7 | 648.75 | 50 | S/R | RHS
11 | 638 | 638.02 | 20 | S/R | RHS
12 | 637.8 | 637.825 | 25 | S/R | RHS
13 | 637.57 | 637.576 | 6 | S/R | RHS
14 | 617.05 | 617.056 | 6 | S/R | RHS
15 | 605.38 | 605.385 | 5 | S/R | RHS
| Total |  | 192

## Solar Blinker (hidden)
SOLAR BLINKER
Sr. No. | Chainage |  | Location | Side | NOS | Remarks
| From | To
1 | 605.4 |  | S/R | RHS | 1
2 | 605.8 |  | S/R | LHS | 1
3 | 606.8 |  | S/R | RHS | 1
4 | 609.9 |  | S/R | BHS | 2
5 | 615.15 |  | V/R | LHS | 1
6 | 617 |  | Median |  | 1
7 | 618.1 |  | S/R | RHS | 1
8 | 620.75 |  | V/R | LHS | 1
9 | 622.3 |  | V/R | BHS | 2
10 | 624.05 |  | V/R | RHS | 1
11 | 625.8 |  | V/R | BHS | 2
12 | 629.2 |  | V/R | RHS | 1
13 | 629.2 |  | S/R | LHS | 1
14 | 630.1 |  | S/R | BHS | 2
15 | 631.2 |  | Median |  | 1
16 | 633.6 |  | V/R | LHS | 1
17 | 635.1 |  | Median |  | 1
18 | 635.45 |  | S/R | BHS | 2
19 | 636.02 |  | V/R | RHS | 1
20 | 636.55 |  | S/R | BHS | 2
21 | 636.9 |  | S/R | BHS | 2
22 | 638 |  | S/R | LHS | 1
23 | 638 |  | S/R | RHS | 1
24 | 638.1 |  | Median |  | 1
25 | 638.1 |  | V/R | RHS | 1
26 | 640.15 |  | S/R | LHS | 1
27 | 640.58 |  | Median | BHS | 2
28 | 641.25 |  | Median | BHS | 2
29 | 643.1 |  | Median | BHS | 2
30 | 646.78 |  | S/R | LHS | 1
31 | 647.1 |  | Median |  | 2
32 | 647.55 |  | S/R | RHS | 1
33 | 647.2 |  | S/R | LHS | 1
34 | 647.7 |  | S/R | LHS | 1
35 | 649.4 |  | S/R | RHS | 1
36 | 650.7 |  | S/R | RHS | 1
37 | 650.95 |  | Median | BHS | 2
38 | 650.98 |  | S/R | RHS | 1
39 | 651.78 |  | S/R | RHS | 1
40 | 652.38 |  | S/R | RHS | 1
41 | 652.8 |  | Median |  | 1
42 | 655.35 |  | Median |  | 1
43 | 656.7 |  | S/R | LHS | 1 | Truck lay bay
44 | 657 |  | S/R | RHS | 1 | Truck lay bay
45 | 657.3 |  | Median |  | 1
46 | 658.35 |  | S/R | BHS | 2
47 | 658.8 |  | S/R | BHS | 2
48 | 659.6 |  | S/R | BHS | 2
49 | 660 |  | S/R | RHS | 1
50 | 659.8 |  | S/R | RHS | 1
51 | 660.7 |  | Median |  | 1
52 | 660.7 |  | S/R | RHS | 1
53 | 660.9 |  | S/R | RHS | 1
54 | 662.8 |  | Median |  | 2
55 | 664.7 |  | Median |  | 2
56 | 666.3 |  | Median |  | 1
57 | 666.55 |  | S/R | LHS | 1
58 | 668.4 |  | Median |  | 1
59 | 670.05 |  | Median |  | 1
60 | 670.6 |  | Median |  | 1
61 | 670.9 |  | Median |  | 1
62 | 671 |  | S/R | LHS | 1
63 | 671.3 |  | S/R | LHS | 1
64 | 671.6 |  | Median |  | 5
65 | 672.8 |  | Median |  | 2
66 | 675.55 |  | Median |  | 4
67 | 676.3 |  | S/R | RHS | 1
68 | 676.45 |  | S/R | LHS | 1
69 | 677 |  | S/R | RHS | 1
|  | TOTAL |  |  | 94

## Rain Water Harvesting (hidden)
Current Status of Initial Improvement works as per Schedule B (As on 08.11.2025) | [6 empty] | Rain Water harvesting
Rain water Harvesting | [6 empty] | Layer | Unit | Nos | Width | Length | Thick | Quantity | Rate | Amount (in Rs.)
Sr.no. | Description | Km. | Side | Quantity in (Nos) |  | Remarks/Observation | RCC Long Wall (M25) | Cum | 2 | 2 | 2.5 | 0.1 |  | 6148.5287 | 0
|  |  |  | Sch-B | Maintenance |  | Slab | Cum | 1 | 2.2 | 2.5 | 0.1 | 0.55 | 77549.7299 | 42652.3515
1 | Rain water Harvesting | 671+100 | RHS | 1 |  | IE/Balance work as per site condition | RCC Short Wall (M25) | Cum | 2 | 1.7 | 2.5 | 0.1 |  | 6148.5287 | 0
|  |  | Balance=>> | 1 | 0 |  | PCC Long Wall | Cum | 2 | 2 | 0.1 | 0.1 |  | 4620.8093 | 0
[7 empty] | PCC Short Wall | Cum | 2 | 1.7 | 0.1 | 0.1 |  | 4620.8093 | 0
[7 empty] | HYSD | MT |  |  |  |  | 0.0055 | 77549.7299 | 426.5235 | Tentative
[7 empty] | Boring for pipe | Rmt | 17.8 |  |  |  |  | 500 | 0
[7 empty] | Coarse sand (1.5–2 mm) | Cum | 1 | 1.55 | 1.55 | 0.3 |  | 405.2849 | 0
[7 empty] | Gravel (5–10 mm) | Cum | 1 | 1.55 | 1.55 | 0.5 |  | 944.16 | 0
[7 empty] | Pebbles (50–150 mm) | Cum | 1 | 1.55 | 1.55 | 1 |  | 944.16 | 0
[7 empty] | Solid PVC pipe (200 mm dia) | Rmt | 1 |  | 17.8 |  |  | 840 | 0
[7 empty] | Bore portion (500 mm dia) | Rmt | 1 |  | 17.8 |  |  | 2100 | 0
[7 empty] | Bore portion filled with gravel | Cum | 1 | 1.57 | 16 | 0.3 |  | 944.16 | 0 | Tentative
[7 empty] | End plug | Nos | 1 |  |  |  |  | 1000 | 0
43078.875