## BOQ
Annexure C3 - Construction of New Major/ Minor Junction
Sr.No. | Item/Description | Unit | Rate | Quantity | Amount | Remarks |  | Code_1
1 | Clearing & Grubbing : Clearing and grubbing road land including uprooting rank vegetation, grass, bushes, shrubs, saplings and trees having girth up to 300 mm, removal of stumps of trees cut earlier and disposal of unserviceable materials and stacking of serviceable material up to a lead of 1000 meters including removal and disposal of top organic soil not exceeding 150 mm in thickness. | Ha. |  | 1 | 0
2 | Excavation : Excavation in Soil using Hydraulic Excavator and Tippers with disposal. (Excavation for roadwork in soil with hydraulic excavator of 0.9 cum bucket capacity including cutting and loading in tippers, trimming bottom and side slopes, in accordance with requirements of lines, grades and cross sections, and transporting to the embankment location within all lifts and lead) | Cum. |  | 630.5 | 0
3 | Embankment Construction with Material Obtained from Borrow Pits Construction of Embankment with approved material obtained from borrow pits, transported with all lifts and leads, including royalty, and spread in uniform layers of not more than 250 mm thickness. The material shall meet the quality requirements specified in MoRTH clause 305, ensuring compliance with gradation, plasticity, and moisture content parameters. Compaction of the subgrade shall achieve a minimum of 97% of Maximum Dry Density (MDD) as per IS 2720 (Part 8), and the earthen shoulders shall be compacted to 95% MDD using mechanical equipment. Grading shall be performed to ensure the required slope, alignment, and stability, with final finishing to the levels specified in the approved drawings. The work includes surface dressing, preparation of shoulders for proper drainage, and all necessary field and laboratory tests, such as field density and moisture content tests, to verify compliance with Table 300-2 of MoRTH specifications. The item covers all costs for material procurement, royalty, transportation, labor, machinery, and incidental works. Safety measures and environmental compliance shall be ensured during execution. The final surface shall be stable, durable, and suitable for traffic loading, conforming to project specifications and ensuring proper integration with adjacent structures. | Cum. |  | 15150 | 0
4 | Subgrade and Earthen Shoulders Construction of subgrade and earthen shoulders with approved material obtained from borrow pits, transported with all lifts and leads, including royalty, and spread in uniform layers of not more than 250 mm thickness. The material shall meet the quality requirements specified in MoRTH Clause 305, ensuring compliance with gradation, plasticity, and moisture content parameters. Compaction of the subgrade shall achieve a minimum of 97% of Maximum Dry Density (MDD) as per IS 2720 (Part 8), and the earthen shoulders shall be compacted to 95% MDD using mechanical equipment. Grading shall be performed to ensure the required slope, alignment, and stability, with final finishing to the levels specified in the approved drawings. The work includes surface dressing, preparation of shoulders for proper drainage, and all necessary field and laboratory tests, such as field density and moisture content tests, to verify compliance with Table 300-2 of MoRTH specifications. The item covers all costs for material procurement, royalty, transportation, labor, machinery, and incidental works. Safety measures and environmental compliance shall be ensured during execution. The final surface shall be stable, durable, and suitable for traffic loading, conforming to project specifications and ensuring proper integration with adjacent structures. | Cum. |  | 13449.35 | 0
5 | Construction of Granular Sub-Base (Grade IV Material) Construction of granular sub-base by providing approved Grade IV material conforming to MoRTH Clause 401 and Table 400-1, with material sourced as per project specifications, including all royalty charges and transportation. The material shall be laid in uniform layers not exceeding 200 mm thickness, using a motor grader with a minimum blade length of 3.05 m and GPS control for precise alignment. Surface preparation, including cleaning and leveling, shall be ensured before placement. Mixing shall be done by an appropriate mechanical mixer with controlled water addition to achieve optimum moisture content. Compaction shall be performed using a vibratory roller of at least 8-10 tonnes to achieve a minimum of 98% Maximum Dry Density (MDD) as determined by IS 2720 (Part 8). Field density tests shall be conducted at intervals of 50 m or as directed by the Engineer-in-Charge to ensure compliance. The work includes preparation of cross slopes and drainage features as per the approved drawings and required gradients. Safety measures, traffic management, and environmental compliance during execution are mandatory. All costs for material, labor, machinery, and testing are included. The final surface shall meet specified levels, alignment, and stability, ensuring durability and proper integration with adjoining layers, as per project drawings and standards. | Cum. |  | 2094.525 | 0 |  |  | #VALUE!
6 | Construction of Wet Mix Macadam (WMM): Construction of Wet Mix Macadam (WMM) by providing approved crushed stone aggregate material conforming to MoRTH Clause 406 , with material sourced as per project specifications, including all royalty charges and transportation. The material shall be laid in uniform layers not exceeding 250 mm thickness, using a motor grader with a minimum blade length of 3.05 m and GPS control for precise alignment. Surface preparation, including cleaning and leveling, shall be ensured before placement. Mixing shall be done by an appropriate mechanical mixer with controlled water addition to achieve optimum moisture content. Compaction shall be performed using a vibratory roller of at least 8-10 tonnes to achieve a minimum of 98% Maximum Dry Density (MDD) as determined by IS 2720 (Part 8). Field density tests shall be conducted at intervals of 50 m or as directed by the Engineer-in-Charge to ensure compliance. The work includes preparation of cross slopes as per the approved drawings and required gradients. Safety measures, traffic management, and environmental compliance during execution are mandatory. All costs for material, labor, machinery, and testing are included. The final surface shall meet specified levels, alignment, and stability, ensuring durability and proper integration with adjoining layers, as per project drawings and standards. | Cum. |  | 2199 | 0 |  |  | #VALUE!
7 | Prime Coat Providing and applying Prime coat with bitumen emulsion using emulsion pressure distributor at the rate of 0.7-1.0 kg per sqm on the prepared bituminous/granular surface cleaned with mechanical broom. | Sqm. |  | 11910 | 0 |  |  | #REF!
8 | Dense Bituminous Macadam: Providing and laying Dense graded bituminous macadam using crushed aggregates of specified grading, premixed with bituminous binder @ 4.5 per cent by weight of total mix and filler, transporting the hot mix to work site, laying with the required grade, level and alignment, rolling with smooth wheeled, vibratory and tandem rollers to achieve the desired compaction as per MoRTH specification clause No. 507 complete in all respects. The work includes preparation of cross slopes as per the approved drawings and required gradients. Safety measures, traffic management, and environmental compliance during execution are mandatory. All costs for material, labor, machinery, and testing are included. The final surface shall meet specified levels, alignment, and stability, ensuring durability and proper integration with adjoining layers, as per project drawings and standards. - Bitumen @ 4.5 per cent of weight of mix. Bitumen Grade Shall be VG-40 | Cum. |  | 982.875 | 0 |  |  | #VALUE!
9 | Tack Coat Providing and applying tack coat with bitumen emulsion using emulsion pressure distributor at the rate of 0.20 kg per sqm on the prepared bituminous/granular surface cleaned with mechanical broom. | Sqm. |  | 30695 | 0 |  |  | #REF!
10 | Bituminous Concrete: Providing and laying bituminous concrete with hot mix plant producing an average output of 75 tonnes per hour using crushed aggregates of specified grading, premixed with bituminous binder @ 5.4 per cent of mix and filler, transporting the hot mix to work site, laying with a paver finisher to the required grade, level and alignment, rolling with smooth wheeled, vibratory and tandem rollers to achieve the desired compaction as per MORTH specification clause No. 509 complete in all respects. The work includes preparation of cross slopes as per the approved drawings and required gradients. Safety measures, traffic management, and environmental compliance during execution are mandatory. All costs for material, labor, machinery, and testing are included. The final surface shall meet specified levels, alignment, and stability, ensuring durability and proper integration with adjoining layers, as per project drawings and standards. - Bitumen @ 5.4% of weight of mix. Bitumen grade shall be VG-40 | Cum. |  | 1069.25 | 0 |  | 60 | #VALUE!
11 | Road studs ( Double Shank)-Providing and fixing of road studs 100*100 mm die cast in aluminium, resistant to corrosive effect of salt and grit fitted with lens reflectors , installed in concrete or asphaltic surface by drilling hole 30 mm upto the depth of 60mm beded in suitable bituminous grout of epocy mortar all per BS 873 part 4:1973/IRC Make :3M only | Nos. |  | 1653 | 0 |  | 180 | #VALUE!
12 | Road Marking-Road Marking over Bitumen Surface-Providing and Laying hot applied thermoplastic road marking strip on Bituminous Surface of specified shade/colour of 2.5 mm thick including 1.5 Refractive index reflectorizing glass beads@ 250gm/sqm. Thickness of 5mm is exclusive of surface applied glass beads as per IRC35:2015. Initial Dry reflectivity RL shall be >250mcd/sqm/lux measured in the initial 7 days and sustained reflectivity RL of 100mcd/sqm/lux and Qd of 100mcd/sqm/lux measured at the end of 2years by means of a Standard Reflectometer of Zehntner, Easylux, Delta make capable of measuring RL & QD both according to IRC35:2015 clause 15.5. The finished surface to be level, uniform, and free from streaks and holes complete as per direction of Engineer-in-charge and in accordance with applicable specifications. (Refer MORTH Clause 803 for technical Specification and Performance for IRC 35:2015). The rate shell be including scrafication of exsiting road marking inckuding primer Source of Road Marking Paint: MoRTH Specifications of Asian or Berger only Source of Drop on Glass Beads: Sovitec; Potters only | Sqm. |  | 2230.5 | 0 |  |  | #VALUE!
13 | Cast-in-Situ Cement Concrete M20 Kerb All charges for the construction of a cast-in-situ cement concrete kerb in M20 grade concrete, with a foundation of M15 grade concrete, as per the approved drawings and technical specifications. The kerb shall be constructed with a top width of 115 mm, a bottom width of 250 mm, and a height of 240 mm. The foundation for the kerb shall be of M15 grade concrete, with a thickness of 150 mm, and shall extend 50 mm beyond the kerb for projection. The foundation concrete shall be placed manually, while the kerb shall be laid using a kerb laying machine to ensure uniformity and alignment. The surface of the kerb shall be finished with one coat of primer and two coats of enamel paint of an approved shade (Asian or equivalent), applied after the concrete has cured and attained the required strength. The work includes all labor, materials, machinery, and overheads required for the construction, finishing, and painting of the kerb. The work shall be executed in accordance with MoRTH's Clause 409 and the relevant IS codes, ensuring proper compaction, curing, and quality control. The final price includes the cost of procurement of cement, aggregates, and other materials, including royalty charges. The cost also covers the labor, machinery, equipment, transportation, laying of concrete, use of kerb laying machines, primer, and enamel paint (2 coats), and all overheads and profit. Relevant Standards: MoRTH Clause: 409 (Cement Concrete for Kerbs, Channels, and Edging) IS 456: Code of Practice for Plain and Reinforced Concrete | Rm. |  | 1000 | 0
|  |  |  | Amount | 0
|  |  |  | GST @ 18% | 0
|  |  |  | Total Amount | 0

## Quantity Summary
Sr.No. | Code | Code_1 | Item/Description | Unit | Quantity | Remarks | Code_1
1 |  |  | New Major junction to be developed at-grade intersections below grade separator/interchange |  |  |  | #REF!
1.01 |  |  | Earthwork in Excavation | Cum | 630.5
1.02 |  |  | Earthwork in filling | Cum | 13449.35
1.03 | 1.01 | 1 | GSB | Cum | 2094.525 |  | #REF!
1.04 | 1.02 | 2 | WMM | Cum | 2199 |  | #REF!
1.05 | 1.03 | 3 | Prime Coat | Sqm | 11910 |  | #REF!
1.06 | 1.04 | 4 | DBM | Cum | 982.875 |  | #REF!
1.07 | 1.05 | 5 | Tack Coat | Sqm | 30695 |  | #REF!
1.08 | 1.06 | 6 | BC | Cum | 1069.25 |  | #REF!
1.09 | 1.1 | 10 | Studs | Nos | 551 |  | #REF!
1.1 | 1.12 | 12 | Road Marking | Sqm | 1115.25 |  | #REF!
1.11 |  |  | Kerb Casting | Rm | 500

## 268.150
Sr.No. | Item/Description | Unit | Number | Length | Width | Depth | Qty. | Remarks
1 | Major Junction (Y- Type)
1.01 | Earthwork in Excavation | Cum. | 0 | 65 | 6 | 0.2 | 0
1.02 | Earthwork in filling
a | Shoulder | Cum. | 1 | 140 | 2 | 0.2 | 56
b | Separator | Cum. | 1 | 50 | 1.2 | 0.35 | 21
77
1.03 | GSB | Cum. | 1 | 0 | 6.3 | 0.15 | 0
1.04 | WMM | Cum. | 1 | 0 | 7 | 0.15 | 0
|  | Cum. | 1 | 0 | 6.3 | 0.15 | 0
0
1.05 | Prime Coat | Sqm | 1 | 0 |  |  | 0
1.06 | Tack Coat-1 | Sqm | 1 | 140 | 12.5 |  | 1750
1.07 | DBM | Cum. | 1 | 140 | 12.5 | 0.075 | 131.25
1.08 | Tack Coat-2 | Sqm | 1 | 140 | 12.5 |  | 1750
1.09 | BC | Cum. | 1 | 140 | 12.5 | 0.05 | 87.5
1.1 | Studs
| Carriageway |  | 2 |  |  |  | 16
| Chevron |  | 1 |  |  |  | 13 | >22 m Diverging
Road Marking
1.11 | Lane Marking | Sqm |  |  |  |  | 47
1.12 | Chevron | Sqm | 3 | 18 |  |  | 54
1.13 | Kerb Island | Rm | 1 | 104 |  |  | 104
| Location | Length(m) | Average width
| 268.14 | 140 | 12.5

## 272.820
Sr.No. | Item/Description | Unit | Number | Length | Width | Depth | Qty. | Remarks
1 | Major Junction (Y- Type)
1.01 | Earthwork in Excavation | Cum. | 1 | 65 | 6 | 0.2 | 78
1.02 | Earthwork in filling
a | Shoulder | Cum. | 1 | 210 | 2 | 0.2 | 84
b | Separator | Cum. | 1 | 35 | 1.2 | 0.35 | 14.7
98.7
1.03 | GSB | Cum. | 1 | 65 | 6.3 | 0.15 | 61.425
1.04 | WMM | Cum. | 1 | 65 | 6 | 0.15 | 58.5
|  | Cum. | 1 | 155 | 6.3 | 0.15 | 146.475
204.975
1.05 | Prime Coat | Sqm | 1 |  |  |  | 1366.5
1.06 | Tack Coat-1 | Sqm | 1 | 210 | 6.5 |  | 1365
1.07 | DBM | Cum. | 1 | 210 | 6.5 | 0.075 | 102.375
1.08 | Tack Coat-2 | Sqm | 1 | 210 | 6.5 |  | 1365
1.09 | BC | Cum. | 1 | 210 | 6.5 | 0.05 | 68.25
1.1 | Studs
| Carriageway |  | 2 |  |  |  | 24
| Chevron |  | 1 |  |  |  | 13 | >22 m Diverging
Road Marking
1.11 | Lane Marking | Sqm |  |  |  |  | 70
1.12 | Chevron | Sqm | 3 | 18 |  |  | 54
124
1.13 | Kerb | Rm | 1 | 35 |  |  | 35
| Location | Length(m) | Average width
| 272.82 | 210 | 6.5

## 307.000
Sr.No. | Item/Description | Unit | Number | Length | Width | Depth | Qty. | Remarks
1 | Major Junction (Y- Type) | [7 empty] | Location | Length(m) | Average width | Remarks
1.01 | Earthwork in Excavation | Cum. | 1 | 80 | 2 | 0.425 | 68 | Tapering | 307 | 45 | 16 | Straight
[5 empty] | Total>>> |  | 68
1.02 | Earthwork in filling | [8 empty] | 80 | 2.575 | Taper
a | Shoulder | Cum. | 1 | 80 | 2 | 0.25 | 40
|  | Cum. | 2 | 45 | 2 | 0.25 | 45
b | Separator | Cum. | 1 | 25 | 2 | 0.35 | 17.5
c | Emb & SG | Cum. | 1 | 80 | 3 | 2 | 480 | Tapering
|  | Cum. | 1 | 45 | 20 | 1 | 900 | Straight
[5 empty] | Total>>> |  | 1482.5
1.03 | GSB | Cum. | 1 | 80 | 2.8 | 0.15 | 33.6 | Tapering
|  | Cum. | 1 | 45 | 20 | 0.15 | 135 | Staright
[5 empty] | Total>>> |  | 168.6
1.04 | WMM | Cum. | 1 | 80 | 2.5 | 0.15 | 30 | Tapering | BC | 0.05
|  | Cum. | 1 | 45 | 16.3 | 0.15 | 110.025 | Straight | DBM | 0.05
[5 empty] | Total>>> |  | 140.025 |  | WMM | 0.15
1.05 | Prime Coat | Sqm. | 1 |  |  |  | 933.5 |  | GSB | 0.15
1.06 | Tack Coat-1 | Sqm. | 1 |  |  |  | 1380 |  | Total>>>> | 0.4
1.07 | DBM | Cum. | 1 | 45 | 16 | 0.075 | 54
|  | Cum. | 1 | 80 | 2.5 | 0.075 | 15
[5 empty] | Total>>>> |  | 69
1.08 | Tack Coat-2 | Sqm | 1 |  |  |  | 1140
1.09 | BC | Cum. | 1 | 45 | 16 | 0.05 | 36
|  | Cum. | 1 | 80 | 2.5 | 0.05 | 10
|  | Cum. | 1 | 40 | 5.5 | 0.05 | 11
[5 empty] | Total>>> |  | 57
1.1 | Studs
| Carriageway | Nos. | 2 |  |  |  | 6
| Chevron | Nos. | 2 |  |  |  | 26 | >22 m Diverging
| pedestrian | Nos. | 1 |  |  |  | 32
|  |  |  | Total>>> |  |  | 64
Road Marking
1.11 | Lane Marking | Sqm. | 1 |  |  |  | 15
1.12 | Chevron | Sqm. | 2 | 18 |  |  | 36 | >22 m Diverging
1.13 | Stop Lettering | Sqm. | 1 | 2.05 | 2.5 |  | 5.125
1.14 | Pedestrain | Sqm. | 1 |  |  |  | 24
1.15 | Stop line | Sqm. | 2 | 16 | 0.3 |  | 9.6
|  |  |  | Total |  |  | 89.725
1.15 | Kerb Island | Rm | 1 | 52 |  |  | 52

## 317.450
Sr.No. | Item/Description | Unit | Number | Length | Width | Depth | Qty. | Remarks
1 | Major Junction (Y- Type) | [7 empty] | Location | Length(m) | Average width
1.01 | Earthwork in Excavation | Cum. | 0 | 65 | 6 | 0.2 | 0 |  | 317.45 | 180 | 16
1.02 | Earthwork in filling
a | Shoulder | Cum. | 1 | 180 | 2 | 0.2 | 72
b | Separator | Cum. | 1 | 70 | 1.2 | 0.35 | 29.4
101.4
1.03 | GSB | Cum. | 1 | 0 | 6.3 | 0.15 | 0
1.04 | WMM | Cum. | 1 | 0 | 7 | 0.15 | 0
|  | Cum. | 1 | 0 | 6.3 | 0.15 | 0
0
1.05 | Prime Coat | Sqm | 1 | 0 |  |  | 0
1.06 | Tack Coat-1 | Sqm | 1 | 180 | 16 |  | 2880
1.07 | DBM | Cum. | 1 | 180 | 16 | 0.075 | 216
1.08 | Tack Coat-2 | Sqm | 1 | 180 | 16 |  | 2880
1.09 | BC | Cum. | 1 | 180 | 16 | 0.05 | 144
1.1 | Studs
| Carriageway |  | 2 |  |  |  | 20
| Chevron |  | 1 |  |  |  | 13 | >22 m Diverging
Road Marking
1.11 | Lane Marking | Sqm | 1 |  |  |  | 60
1.12 | Chevron | Sqm | 1 | 18 |  |  | 18 | >22 m Diverging
1.13 | Kerb Island | Rm | 1 | 144 |  |  | 144

## 326.500
AREA JUNCTION
Sr.No. | Item | Unit | Number | Area | Thk. | Qty. | Remarks | Sr.No. | Item/Description | Unit | Number | Length | Width | Depth | Qty. | Remarks | Item | Maj. J (X-Type) (2-Lane)
1 | Major Junction (X- Type) (2-Lane) |  | 1 |  |  |  |  | 1 | Major Junction (X- Type) (2-Lane) | [7 empty] | Sub Grade | 5050
1.01 | GSB | Cum | 1 | 5050 | 0.15 | 757.5 |  |  | For SG, GSB & WMM | [7 empty] | GSB | 5050
1.02 | WMM | Cum | 1 | 5050 | 0.15 | 757.5 |  | 1.01 | Tapered Lane | Sqm. | 2 | 110 | 2.5 |  | 550 |  | WMM | 5050
1.03 | Prime Coat | Sqm | 1 | 3675 | 1 | 3675 |  | 1.02 | Auxilary lane | Sqm. | 2 | 240 | 5 |  | 2400 |  | DBM | 3675
1.04 | DBM | Cum | 1 | 3675 | 0.05 | 183.75 |  | 1.03 | Curve | Sqm. | 4 | 15 | 5 |  | 300 |  | BC | 3675
1.05 | Tack Coat | Sqm | 2 | 3675 | 1 | 3675 |  | 1.04 | Cross Road | Sqm. | 2 | 100 | 9 |  | 1800
1.06 | BC | Cum | 1 | 3675 | 0.05 | 183.75 |  |  | For DBM & BC
1.07 | Construction of New E.S | Cum | 1 | 2190 | 0.2 | 438 |  | 1.05 | Tapered Lane | Sqm. | 2 | 110 | 1.75 |  | 385
1.08 | Sub Grade | Cum | 1 | 5050 | 0.5 | 2525 |  | 1.06 | Auxilary lane | Sqm. | 2 | 240 | 3.5 |  | 1680
1.08 | Embankment | Cum | 1 | 5050 | 1.5 | 7575 |  | 1.07 | Curve | Sqm. | 4 | 15 | 3.5 |  | 210
1.08 | Studs | Nos | 1 |  |  | 47 |  | 1.08 | Cross Road | Sqm. | 2 | 100 | 7 |  | 1400
1.1 | Pedestrian Marking | Sqm | 1 |  |  | 21 |  | 1.09 | For Dismantling of Existing Shoulder | Sqm. | 2 | 350 | 1.5 |  | 1050
1.11 | Road Marking | Sqm | 1 |  |  | 102.6 |  | 1.1 | For New Earthen Shoulder | Sqm. | 4 | 365 | 1.5 |  | 2190
b | Stop Lettering | Sqm | 2 |  |  | 10.25 |  | 1.11 | Studs Chevron | Nos | 2 |  |  |  | 36
c | Stop Line | Sqm | 2 |  |  | 4.2 |  | 1.12 | Studs pavement | Nos | 2 |  |  |  | 11
[6 empty] | 138.05 |  | 1.13 | Road Marking | [5 empty] | 66.6
[8 empty] | 1.14 | Chevron | [5 empty] | 36

## 344.770
Sr.No. | Item/Description | Unit | Number | Length | Width | Depth | Qty. | Remarks
1 | Major Junction (Y- Type) | [7 empty] | Location | Length(m) | Average width | Remarks
1.01 | Earthwork in Excavation | Cum. | 1 | 50 | 2 | 0.425 | 42.5 | Tapering | 344.77 | 30 | 8 | Straight
[5 empty] | Total>>> |  | 42.5
1.02 | Earthwork in filling | [8 empty] | 50 | 2.575 | Taper
a | Shoulder | Cum. | 1 | 50 | 1.5 | 0.25 | 18.75
[5 empty] | Total>>> |  | 18.75
1.03 | GSB | Cum. | 1 | 50 | 2.8 | 0.15 | 21 | Tapering
[5 empty] | Total>>> |  | 21
1.04 | WMM | Cum. | 1 | 80 | 2.5 | 0.15 | 30 | Tapering | BC | 0.05
[5 empty] | Total>>> |  | 30 |  | WMM | 0.15
1.05 | Prime Coat | Sqm. | 1 |  |  |  | 200 |  | GSB | 0.15
1.06 | Tack Coat-1 | Sqm. | 1 |  |  |  | 187.5 |  | Total>>>> | 0.35
|  | Cum. | 1 | 50 | 2.5 | 0.075 | 9.375
[5 empty] | Total>>>> |  | 9.375
1.08 | Tack Coat-2 | Sqm | 1 |  |  |  | 965
1.09 | BC | Cum. | 2 | 50 | 8 | 0.05 | 40
|  | Cum. | 1 | 30 | 5.5 | 0.05 | 8.25
[5 empty] | Total>>> |  | 48.25
1.1 | Studs
| Carriageway | Nos. | 2 |  |  |  | 4
| Chevron | Nos. | 0 |  |  |  | 0 | >22 m Diverging
| pedestrian | Nos. | 1 |  |  |  | 32
|  |  |  | Total>>> |  |  | 36
Road Marking
1.11 | Lane Marking | Sqm. | 1 |  |  |  | 10
1.13 | Stop Lettering | Sqm. | 1 | 2.05 | 2.5 |  | 5.125
1.14 | Pedestrain | Sqm. | 1 |  |  |  | 12
1.15 | Stop line | Sqm. | 2 | 8 | 0.3 |  | 4.8
|  |  |  | Total |  |  | 31.925
1.15 | Kerb Island | Rm | 0 | 52 |  |  | 0

## 347.600 MN
Sr.No. | Item/Description | Unit | Number | Length | Width | Depth | Qty. | Remarks
1 | Major Junction (Y- Type) | [7 empty] | Location | Length(m) | Average width
1.01 | Earthwork in Excavation | Cum. | 0 | 65 | 6 | 0.2 | 0 |  | 347.6 | 40 | 8.75
1.02 | Earthwork in filling
a | Shoulder | Cum. | 0 | 40 | 2 | 0.2 | 0
b | Separator | Cum. | 0 | 70 | 1.2 | 0.35 | 0
0
1.03 | GSB | Cum. | 1 | 0 | 6.3 | 0.15 | 0
1.04 | WMM | Cum. | 1 | 40 | 4 | 0.15 | 24
24
1.05 | Prime Coat | Sqm | 1 | 0 |  |  | 160
1.06 | Tack Coat-1 | Sqm | 0 | 40 | 8.75 |  | 0
1.07 | DBM | Cum. | 0 | 40 | 8.75 | 0.05 | 0
1.08 | Tack Coat-2 | Sqm | 1 | 40 | 8.75 |  | 350
1.09 | BC | Cum. | 1 | 40 | 8.75 | 0.05 | 17.5
1.1 | Studs
| Carriageway |  | 2 |  |  |  | 4
| Chevron |  | 0 |  |  |  | 0 | >22 m Diverging
| Pedestrian | [5 empty] | 18
Road Marking
1.11 | Lane Marking | Sqm | 1 |  |  |  | 13
1.12 | Chevron | Sqm | 0 | 0 |  |  | 0 | >22 m Diverging
| Pedestrain | Sqm. | 1 |  |  |  | 13.5
| Stop line | Sqm. | 2 | 8.75 | 0.3 |  | 5.25
| Stop lettering | Sqm | 1 | 2.05 | 2.5 |  | 5.125
1.13 | Kerb Island | Rm | 0 | 0 |  |  | 0

## 356.300
Sr.No. | Item/Description | Unit | Number | Length | Width | Depth | Qty. | Remarks
1 | Major Junction (Y- Type) | [7 empty] | Location | Length(m) | Average width | Remarks
1.01 | Earthwork in Excavation | Cum. | 1 | 50 | 2 | 0.425 | 42.5 | Tapering | 356.3 | 30 | 8 | Straight
[5 empty] | Total>>> |  | 42.5
1.02 | Earthwork in filling | [8 empty] | 50 | 2.575 | Taper
a | Shoulder | Cum. | 1 | 50 | 2 | 0.25 | 25
[5 empty] | Total>>> |  | 25
1.03 | GSB | Cum. | 1 | 50 | 2.8 | 0.15 | 21 | Tapering
[5 empty] | Total>>> |  | 21
1.04 | WMM | Cum. | 1 | 80 | 2.5 | 0.15 | 30 | Tapering | BC | 0.05
[5 empty] | Total>>> |  | 30 |  | DBM | 0.05
1.05 | Prime Coat | Sqm. | 1 |  |  |  | 200 |  | WMM | 0.15
1.06 | Tack Coat-1 | Sqm. | 1 |  |  |  | 187.5 |  | GSB | 0.15
|  | Cum. | 1 | 50 | 2.5 | 0.075 | 9.375 |  |  | 0.4
[5 empty] | Total>>>> |  | 9.375
1.08 | Tack Coat-2 | Sqm | 1 |  |  |  | 965
1.09 | BC | Cum. | 2 | 50 | 8 | 0.05 | 40
|  | Cum. | 1 | 30 | 5.5 | 0.05 | 8.25
[5 empty] | Total>>> |  | 48.25
1.1 | Studs
| Carriageway | Nos. | 2 |  |  |  | 4
| Chevron | Nos. | 0 |  |  |  | 0 | >22 m Diverging
| pedestrian | Nos. | 1 |  |  |  | 32
|  |  |  | Total>>> |  |  | 36
Road Marking
1.11 | Lane Marking | Sqm. | 1 |  |  |  | 10
1.13 | Stop Lettering | Sqm. | 1 | 2.05 | 2.5 |  | 5.125
1.14 | Pedestrain | Sqm. | 1 |  |  |  | 12
1.15 | Stop line | Sqm. | 2 | 8 | 0.3 |  | 4.8
|  |  |  | Total |  |  | 31.925
1.15 | Kerb Island | Rm | 0 | 52 |  |  | 0

## 360.100
Sr.No. | Item/Description | Unit | Number | Length | Width | Depth | Qty. | Remarks
1 | Major Junction (Y- Type) | [7 empty] | Location | Length(m) | Average width | Remarks
1.01 | Earthwork in Excavation | Cum. | 1 | 70 | 2 | 0.425 | 59.5 | Tapering | 360.1 | 40 | 30 | Straight
[5 empty] | Total>>> |  | 59.5
1.02 | Earthwork in filling | [8 empty] | 70 | 5 | Taper
a | Shoulder | Cum. | 1 | 70 | 2 | 0.25 | 35
| Earth work in filling | Cum. | 1 | 70 | 5 | 1.5 | 525
[5 empty] | Total>>> |  | 560
1.03 | GSB | Cum. | 1 | 70 | 5 | 0.15 | 52.5 | Tapering
[5 empty] | Total>>> |  | 52.5
1.04 | WMM | Cum. | 1 | 80 | 5 | 0.15 | 60 | Tapering | BC | 0.05
[5 empty] | Total>>> |  | 60 |  | DBM | 0.05
1.05 | Prime Coat | Sqm. | 1 |  |  |  | 400 |  | WMM | 0.15
1.06 | Tack Coat-1 | Sqm. | 1 |  |  |  | 210 |  | GSB | 0.15
|  | Cum. | 1 | 70 | 3 | 0.05 | 10.5 |  |  | 0.4
[5 empty] | Total>>>> |  | 10.5
1.08 | Tack Coat-2 | Sqm | 1 |  |  |  | 1620
1.09 | BC | Cum. | 2 | 70 | 3 | 0.05 | 21
|  | Cum. | 1 | 40 | 30 | 0.05 | 60
[5 empty] | Total>>> |  | 81
1.1 | Studs
| Carriageway | Nos. | 2 |  |  |  | 4
| Chevron | Nos. | 1 |  |  |  | 13 | >22 m Diverging
| pedestrian | Nos. | 1 |  |  |  | 60
|  |  |  | Total>>> |  |  | 77
Road Marking
1.11 | Lane Marking | Sqm. | 1 |  |  |  | 13
1.13 | Stop Lettering | Sqm. | 2 | 2.05 | 2.5 |  | 10.25
1.14 | Pedestrain | Sqm. | 1 |  |  |  | 45
1.15 | Stop line | Sqm. | 2 | 30 | 0.3 |  | 18
|  |  |  | Total |  |  | 86.25
1.15 | Kerb Island | Rm | 1 | 50 |  |  | 50
| Kerb dismantling | Rm | 1 | 50 |  |  | 50

## 373.950
Sr.No. | Item/Description | Unit | Number | Length | Width | Depth | Qty. | Remarks
1 | Major Junction (Y- Type) | [7 empty] | Location | Length(m) | Average width | Remarks
1.01 | Earthwork in Excavation | Cum. | 2 | 50 | 2 | 0.425 | 85 | Tapering | 373.95 | 40 | 17.25 | Straight
[5 empty] | Total>>> |  | 85
1.02 | Earthwork in filling | [8 empty] | 50 | 5 | Taper
a | Shoulder | Cum. | 2 | 50 | 2 | 0.25 | 50
| Earth work in filling | Cum. | 2 | 50 | 5 | 1.68 | 840
[5 empty] | Total>>> |  | 890
1.03 | GSB | Cum. | 2 | 50 | 5 | 0.15 | 75 | Tapering
[5 empty] | Total>>> |  | 75
1.04 | WMM | Cum. | 2 | 50 | 5 | 0.15 | 75 | Tapering | BC | 0.05
[5 empty] | Total>>> |  | 75 |  | DBM | 0.05
1.05 | Prime Coat | Sqm. | 1 |  |  |  | 500 |  | WMM | 0.15
1.06 | Tack Coat-1 | Sqm. | 1 |  |  |  | 300 |  | GSB | 0.15
| DBM | Cum. | 2 | 50 | 3 | 0.05 | 15 |  |  | 0.4
[5 empty] | Total>>>> |  | 15
1.08 | Tack Coat-2 | Sqm | 1 |  |  |  | 990
1.09 | BC | Cum. | 2 | 50 | 3 | 0.05 | 15
|  | Cum. | 1 | 40 | 17.25 | 0.05 | 34.5
[5 empty] | Total>>> |  | 49.5
1.1 | Studs
| Carriageway | Nos. | 1 |  |  |  | 4
| Chevron | Nos. | 1 |  |  |  | 13
| pedestrian | Nos. | 1 |  |  |  | 17
|  |  |  | Total>>> |  |  | 34
Road Marking
1.11 | Lane Marking | Sqm. | 1 |  |  |  | 13
1.13 | Stop Lettering | Sqm. | 2 | 2.05 | 2.5 |  | 10.25
1.14 | Pedestrain | Sqm. | 1 |  |  |  | 25.875
1.15 | Stop line | Sqm. | 2 | 17.25 | 0.3 |  | 10.35
|  |  |  | Total |  |  | 59.475
1.15 | Kerb Island | Rm | 1 | 0 |  |  | 0
| Kerb dismantling | Rm | 1 | 0 |  |  | 0

## 380.080
Sr.No. | Item/Description | Unit | Number | Length | Width | Depth | Qty. | Remarks
1 | Major Junction (Y- Type) | [7 empty] | Location | Length(m) | Average width | Remarks
1.01 | Earthwork in Excavation | Cum. | 2 | 0 | 2 | 0.425 | 0 | Tapering | 373.95 | 35 | 14 | Straight
[5 empty] | Total>>> |  | 0
1.02 | Earthwork in filling | [8 empty] | 0 | 5 | Taper
a | Shoulder | Cum. | 2 | 0 | 0 | 0.25 | 0
| Earth work in filling | Cum. | 2 | 0 | 0 | 3 | 0
[5 empty] | Total>>> |  | 0
1.03 | GSB | Cum. | 2 | 0 | 0 | 0.15 | 0 | Tapering
[5 empty] | Total>>> |  | 0
1.04 | WMM | Cum. | 2 | 0 | 0 | 0.15 | 0 | Tapering | BC | 0.05
[5 empty] | Total>>> |  | 0 |  | DBM | 0.05
1.05 | Prime Coat | Sqm. | 1 |  |  |  | 0 |  | WMM | 0.15
1.06 | Tack Coat-1 | Sqm. | 1 |  |  |  | 0 |  | GSB | 0.15
| DBM | Cum. | 2 | 0 | 3 | 0.05 | 0 |  |  | 0.4
[5 empty] | Total>>>> |  | 0
1.08 | Tack Coat-2 | Sqm | 1 |  |  |  | 180
1.09 | BC | Cum. | 2 | 30 | 3 | 0.05 | 9
|  | Cum. | 1 | 0 | 14 | 0.05 | 0
[5 empty] | Total>>> |  | 9
1.1 | Studs
| Carriageway | Nos. | 1 |  |  |  | 4
| Chevron | Nos. | 1 |  |  |  | 13
| pedestrian | Nos. | 1 |  |  |  | 14
|  |  |  | Total>>> |  |  | 31
Road Marking
1.11 | Lane Marking | Sqm. | 1 |  |  |  | 12
1.13 | Stop Lettering | Sqm. | 1 | 2.05 | 2.5 |  | 5.125
1.14 | Pedestrain | Sqm. | 1 |  |  |  | 21
1.15 | Stop line | Sqm. | 2 | 14 | 0.3 |  | 8.4
|  |  |  | Total |  |  | 46.525
1.15 | Kerb Island | Rm | 1 | 0 |  |  | 0
| Kerb dismantling | Rm | 1 | 0 |  |  | 0

## 389.400
AREA JUNCTION
Sr.No. | Item | Unit | Number | Area | Thk. | Qty. | Remarks | Sr.No. | Item/Description | Unit | Number | Length | Width | Depth | Qty. | Remarks | Item | Maj. J (T-Type) (2-Lane)
1 | Major Junction (X- Type) (2-Lane) |  | 1 |  |  |  |  | 1 | Major Junction (T- Type) (2-Lane) | [7 empty] | Sub Grade | 5050
1.01 | GSB | Cum | 1 | 5050 | 0.15 | 757.5 |  |  | For SG, GSB & WMM | [7 empty] | GSB | 5050
1.02 | WMM | Cum | 1 | 5050 | 0.15 | 757.5 |  | 1.01 | Tapered Lane | Sqm. | 2 | 110 | 2.5 |  | 550 |  | WMM | 5050
1.03 | Prime Coat | Sqm | 1 | 3675 | 1 | 3675 |  | 1.02 | Auxilary lane | Sqm. | 2 | 240 | 5 |  | 2400 |  | DBM | 3675
1.04 | DBM | Cum | 1 | 3675 | 0.05 | 183.75 |  | 1.03 | Curve | Sqm. | 4 | 15 | 5 |  | 300 |  | BC | 3675
1.05 | Tack Coat | Sqm | 2 | 3675 | 1 | 3675 |  | 1.04 | Cross Road | Sqm. | 2 | 100 | 9 |  | 1800
1.06 | BC | Cum | 1 | 3675 | 0.05 | 183.75 |  |  | For DBM & BC
1.07 | Construction of New E.S | Cum | 1 | 2190 | 0.2 | 438 |  | 1.05 | Tapered Lane | Sqm. | 2 | 110 | 1.75 |  | 385
1.08 | Sub Grade | Cum | 1 | 5050 | 0.5 | 2525 |  | 1.06 | Auxilary lane | Sqm. | 2 | 240 | 3.5 |  | 1680
1.08 | Embankment | Cum | 1 | 5050 | 1.5 | 7575 |  | 1.07 | Curve | Sqm. | 4 | 15 | 3.5 |  | 210
1.09 | Studs | Nos | 1 |  |  | 47 |  | 1.08 | Cross Road | Sqm. | 2 | 100 | 7 |  | 1400
1.1 | Pedestrian Marking | Sqm | 1 |  |  | 21 |  | 1.09 | For Dismantling of Existing Shoulder | Sqm. | 2 | 350 | 1.5 |  | 1050
1.11 | Road Marking | Sqm | 1 |  |  | 102.6 |  | 1.1 | For New Earthen Shoulder | Sqm. | 4 | 365 | 1.5 |  | 2190
b | Stop Lettering | Sqm | 2 |  |  | 10.25 |  | 1.11 | Studs Chevron | Nos | 2 |  |  |  | 36
c | Stop Line | Sqm | 2 |  |  | 4.2 |  | 1.12 | Studs pavement | Nos | 2 |  |  |  | 11
[6 empty] | 138.05 |  | 1.13 | Road Marking | [5 empty] | 66.6
[8 empty] | 1.14 | Chevron | [5 empty] | 36

## 394.000
Sr.No. | Item/Description | Unit | Number | Length | Width | Depth | Qty. | Remarks
1 | Major Junction (Y- Type) | [7 empty] | Location | Length(m) | Average width | Remarks
1.01 | Earthwork in Excavation | Cum. | 4 | 50 | 2 | 0.425 | 170 | Tapering | 373.95 | 40 | 14 | Straight
[5 empty] | Total>>> |  | 170
1.02 | Earthwork in filling | [8 empty] | 50 | 5 | Taper
a | Shoulder | Cum. | 4 | 50 | 2 | 0.25 | 100
| Earth work in filling | Cum. | 4 | 50 | 5 | 2.9 | 2900
[5 empty] | Total>>> |  | 3000
1.03 | GSB | Cum. | 4 | 50 | 4 | 0.15 | 120 | Tapering
[5 empty] | Total>>> |  | 120
1.04 | WMM | Cum. | 2 | 50 | 4 | 0.15 | 60 | Tapering | BC | 0.05
[5 empty] | Total>>> |  | 60 |  | DBM | 0.05
1.05 | Prime Coat | Sqm. | 1 |  |  |  | 400 |  | WMM | 0.15
1.06 | Tack Coat-1 | Sqm. | 1 |  |  |  | 700 |  | GSB | 0.15
| DBM | Cum. | 4 | 50 | 3.5 | 0.05 | 35 |  |  | 0.4
[5 empty] | Total>>>> |  | 35
1.08 | Tack Coat-2 | Sqm | 1 |  |  |  | 1160
1.09 | BC | Cum. | 1 | 40 | 14 | 0.05 | 28
|  | Cum. | 4 | 50 | 3 | 0.05 | 30
[5 empty] | Total>>> |  | 58
1.1 | Studs
| Carriageway | Nos. | 1 |  |  |  | 4
| Chevron | Nos. | 0 |  |  |  | 0
| pedestrian | Nos. | 1 |  |  |  | 14
|  |  |  | Total>>> |  |  | 18
Road Marking
1.11 | Lane Marking | Sqm. | 1 |  |  |  | 13
1.13 | Stop Lettering | Sqm. | 1 | 2.05 | 2.5 |  | 5.125
1.14 | Pedestrain | Sqm. | 1 |  |  |  | 21
1.15 | Stop line | Sqm. | 2 | 14 | 0.3 |  | 8.4
|  |  |  | Total |  |  | 47.525
1.15 | Kerb Island | Rm | 1 | 0 |  |  | 0
| Kerb dismantling | Rm | 1 | 0 |  |  | 0

## 409.630
Sr.No. | Item/Description | Unit | Number | Length | Width | Depth | Qty. | Remarks
1 | Major Junction (Y- Type) | [7 empty] | Location | Length(m) | Average width | Remarks
1.01 | Earthwork in Excavation | Cum. | 2 | 50 | 2 | 0.425 | 85 | Tapering | 373.95 | 40 | 16.75 | Straight
[5 empty] | Total>>> |  | 85
1.02 | Earthwork in filling | [8 empty] | 50 | 5 | Taper
a | Shoulder | Cum. | 2 | 50 | 2 | 0.25 | 50
| Earth work in filling | Cum. | 2 | 50 | 5 | 2.25 | 1125
[5 empty] | Total>>> |  | 1175
1.03 | GSB | Cum. | 2 | 50 | 4 | 0.15 | 60 | Tapering
[5 empty] | Total>>> |  | 60
1.04 | WMM | Cum. | 2 | 50 | 4 | 0.15 | 60 | Tapering | BC | 0.05
[5 empty] | Total>>> |  | 60 |  | DBM | 0.05
1.05 | Prime Coat | Sqm. | 1 |  |  |  | 400 |  | WMM | 0.15
1.06 | Tack Coat-1 | Sqm. | 1 |  |  |  | 350 |  | GSB | 0.15
| DBM | Cum. | 2 | 50 | 3.5 | 0.05 | 17.5 |  |  | 0.4
[5 empty] | Total>>>> |  | 17.5
1.08 | Tack Coat-2 | Sqm | 1 |  |  |  | 670
1.09 | BC | Cum. | 1 | 40 | 16.75 | 0.05 | 33.5
|  | Cum. | 0 | 0 | 3 | 0.05 | 0
[5 empty] | Total>>> |  | 33.5
1.1 | Studs
| Carriageway | Nos. | 1 |  |  |  | 4
| Chevron | Nos. | 0 |  |  |  | 0
| Pedestrian | Nos. | 1 |  |  |  | 17
|  |  |  | Total>>> |  |  | 21
Road Marking
1.11 | Lane Marking | Sqm. | 1 |  |  |  | 13
1.13 | Stop Lettering | Sqm. | 1 | 2.05 | 2.5 |  | 5.125
1.14 | Pedestrain | Sqm. | 1 |  |  |  | 25.125
1.15 | Stop line | Sqm. | 2 | 16.75 | 0.3 |  | 10.05
|  |  |  | Total |  |  | 53.3
1.15 | Kerb Island | Rm | 1 | 0 |  |  | 0
| Kerb dismantling | Rm | 1 | 0 |  |  | 0

## 411.968
Sr.No. | Item/Description | Unit | Number | Length | Width | Depth | Qty. | Remarks
1 | Major Junction (Y- Type) | [7 empty] | Location | Length(m) | Average width | Remarks
1.01 | Earthwork in Excavation | Cum. | 0 | 50 | 2 | 0.425 | 0 | Tapering | 373.95 | 40 | 15 | Straight
[5 empty] | Total>>> |  | 0
1.02 | Earthwork in filling | [8 empty] | 50 | 2 | Taper
a | Shoulder | Cum. | 1 | 50 | 2 | 0.95 | 95
[5 empty] | Total>>> |  | 95
1.03 | GSB | Cum. | 0 | 50 | 4 | 0.15 | 0 | Tapering
[5 empty] | Total>>> |  | 0
1.04 | WMM | Cum. | 0 | 50 | 4 | 0.15 | 0 | Tapering | BC | 0.05
[5 empty] | Total>>> |  | 0 |  | DBM | 0.05
1.05 | Prime Coat | Sqm. | 1 |  |  |  | 0 |  | WMM | 0.15
1.06 | Tack Coat-1 | Sqm. | 1 |  |  |  | 0 |  | GSB | 0.15
| DBM | Cum. | 0 | 50 | 3.5 | 0.05 | 0 |  |  | 0.4
[5 empty] | Total>>>> |  | 0
1.08 | Tack Coat-2 | Sqm | 1 |  |  |  | 0
1.09 | BC | Cum. | 0 | 40 | 15 | 0.05 | 0
|  | Cum. | 0 | 0 | 3 | 0.05 | 0
[5 empty] | Total>>> |  | 0
1.1 | Studs
| Carriageway | Nos. | 1 |  |  |  | 4
| Chevron | Nos. | 0 |  |  |  | 0
| Pedestrian | Nos. | 1 |  |  |  | 15
|  |  |  | Total>>> |  |  | 19
Road Marking
1.11 | Lane Marking | Sqm. | 1 |  |  |  | 13
1.13 | Stop Lettering | Sqm. | 1 | 2.05 | 2.5 |  | 5.125
1.14 | Pedestrain | Sqm. | 1 |  |  |  | 22.5
1.15 | Stop line | Sqm. | 2 | 15 | 0.3 |  | 9
|  |  |  | Total |  |  | 49.625
1.15 | Kerb Island | Rm | 1 | 0 |  |  | 0
| Kerb dismantling | Rm | 1 | 0 |  |  | 0

## MB-Junction_Sch-B
Clause 4 of Sch B :- Intersections and Grade Separated Intersections | [6 empty] | Transverse Bar Mark | 15
Sr.No. | Design Chainage (km) | Type of Junction | Leads to |  | Median Opening | Category of Cross Road | Carriageway Width (m) of Cross Road | Length of Cross Road
|  |  | LHS | RHS |  |  |  | LHS | RHS
1 | 326.5 | X | Shahjanahnpur | Chauhanpur | Yes | MDR | 2 Lane | 100 | 100 | 2
Clause 4.2 (a) At-grade Intersections below Grade Separator/Interchanges a) New Junction to be developed due to New Proposal of Grade Separator (major)
Sr.No. | Existing Chainage (km) | Type of Junction | Leads to |  | Median Opening | Category of Cross Road | Carriageway Width (m) of Cross Road | Length (m) of cross Road to be developed
|  |  | LHS | RHS |  |  |  | LHS | RHS
1 | 268.15 | Y | - | Faridpur | Yes | Bypass Start | 2 Lane |  | 100 | 1
2 | 272.82 | Y | - | Faridpur | Yes | Bypass End | 2 Lane |  | 100 | 1
3 | 307 | Y | - | Tilhar | Yes | Bypass End | 2 Lane |  | 100 | 1
4 | 317.45 | Y | Gopalpur/Pilibhit | - | Yes | Nagariya Mod | 2 Lane | 100 |  | 1
5 | 344.77 | T | - | Dadraul Village | Yes | Cross Road | 2 Lane |  | 100 | 1
6 | 356.3 | Y | - | Jangbahadur Ganj | Yes | Bypass Start | 2 Lane |  | 100 | 1
7 | 360.1 | Y | - | Jangbahadur Ganj | Yes | Bypass End | 2 Lane |  | 100 | 1
8 | 373.95 | Y | - | Maigalganj | Yes | Bypass Start | 2 Lane |  | 100 | 1
9 | 380.08 | Y | - | Maigalganj | Yes | Bypass End | 2 Lane |  | 100 | 1
10 | 389.4 | Y | - | Maholi | Yes | Village road | 3.5 |  | 100 | 1
11 | 411.968 | Y | - | Sitapur | Yes | Bypass Start | 2 Lane | 100 |  | 1
Clause 4.2 (b) At-grade Intersections below Grade Separator/Interchanges b) New Junction to be developed due to New Proposal of Grade Separator (minor)
Sr.No. | Existing Chainage (km) | Type of Junction | Leads to |  | Median Opening | Category of Cross Road | Carriageway Width (m) of Cross Road | Length (m) of cross Road to be developed
|  |  | LHS | RHS |  |  |  | LHS | RHS
1 | 347.6 | T | Ucchauliya | - | Yes | Village Road | 5m | 100
2 | 394 | X | Village Road | Village Road | Yes | Village Road | 5m | 100 | 100
3 | 409.63 | X | T | - | Village Road | Yes | 5m | 100