## Payment weightage (Scope of Wo)
Payment Schedule
Contract Value:
S No | Stage for payment | Unit | Percentage weightage | Amount
1 | Dismantling of existing Minor Bridge | LS | 6.002%
2 | Excavation | Rmt | 1.434%
3 | Foundation : On completion of the foundation work including PCC & Raft
3.a | PCC including Ground improvement if required complete in all respect | Rmt | 1.875%
3.b | Open Foundation including Steel fixing, Concreting etc complete in all respect. | Rmt | 24.28%
4 | Sub- Structure: On completion of wall upto slab
4.a | Wall Shaft Height upto2m Including Concreting, Steel etc complete in all respect | Rmt | 9.463%
4.b | Wall Shaft Height from2m to Slab top Including Concreting, Steel etc complete in all respect | Rmt | 6.304%
4.c | Rebaring work with Dowel bar | Rmt | 0.637%
5 | Super-structure: On completion of the superstructure in all respects
5.a | Top slab Casting including Including Concreting, Steel etc complete in all respect | Rmt | 22.07%
6 | Misc. Work Like Approach Construction, Approach Slab, Wearing Coat, Footpath , Retaining Wall etc Completed in all respect
6.a | Approach Slab including PCC etc complete in all respect | Nos | 1.357%
6.b | Wearing Coat including Mastic Sheet | Sqm | 5.163%
6.c | Restoration of existing MNB Toe wall, Quadrant Pitching, Floor apron etc all complete | LS | 8.045%
6.d | Crash Barrier including painting etc all complete | Rmt | 1.449%
6.e | Construction of Flexible Approach including Backfilling, Filter media, Restoration of existing maincarrageway and all misc work road marking, kerb, Kerb painting etc complete in all respect | LS | 8.113%
7 | Completion of all Structure Schedule Test and Others Misc work | LS | 2.387%
8 | Casting and Fixing of Km , 5th Km stone with Painting
8.a | 5th Km stone Casting, Fixing , Painting complete in all respect | Nos | 0.464%
8.b | Km stone Casting, Fixing , Painting complete in all respect | Nos | 0.946%
Total |  |  | 100%
Total Amount in Cr.

## BoQ
Annexure C3 - BoQ Minor Bridge Work
Name of Work : TOLLING, OPERATION, MAINTENANCE & TRANSFER OF SIX LANE WITH PAVED SHOULDER OF GUNDUGOLANU - CHINNA AVUTAPALLI SECTION FROM EXISTING KM 1023+496 TO 1076+280 OF NH-16 IN THE STATE OF ANDHRA PRADESH
BoQ Item No. | Specifications | Description of Items | Total Qty | Rate | Unit | Amount (In Rs) | Remarks
1 |  | Dismantling & Excavation of Existing Bridge
A |  | Prestressed / Reinforced cement concrete grade M-20 & above grade (Mechanical Means) | 541.716 |  | Cum | 0
B |  | Dismantling of Flexible Pavements (Dismantling of flexible pavements and disposal of dismantled materials up to a lead of 1000 metres, stacking serviceable and unserviceable materials separately) - Bituminous coarse | 33.7171 |  | Cum | 0
C |  | Dismantling Kerb Stone (Dismantling kerb stone by manual means and disposal of dismantled material with all lifts and up to a lead of 1000 metre) | 60 |  | Rmt | 0
D |  | Dismantling of CC Crash Barrier | 10.8986 |  | Cum | 0
E |  | Excavation for foundation by mechanical means in earth, soils of all types, sand, gravel, soft murum including shoring and strutting as necessary and disposing off excavated stuff as directed etc. complete. | 288.765 |  | Cum | 0
F |  | Excavation for foundation by mechanical means in hard murum including shoring and strutting as necessary and disposing off excavated stuff as directed etc. complete. | 192.51 |  | Cum | 0
TOTAL AMOUNT | [5 empty] | 0
2 |  | PCC & Raft Foundation Work
A |  | PCC M-15 Providing and laying in situ/ready mix/ready mix M15 cement concr ete of trap/granite/quartzite/gneiss metal in foundation including necessary centering, formwork, bailing out water , compacting and cur ing etc. complete. (with fully automatic micr o pr ocessor based PLC w ith SCADA enabled w ith r ever sible dr um type mixer /concrete batch mix plant (pan mixer ) with natural /artifical sand) | 39.246 |  | Cum | 0
B |  | Raft Foundation Providing and laying in situ M35 controlled cement concrete of trap/ granite/ quartzite/ gneiss metal for RCC work in Box/solid/ deck slab etc. including ramming, vibrating, curing, formwork, centering and finishing in cement plaster excluding reinforcement etc. complete. | 211.761 |  | Cum | 0
C |  | Raft Foundation @ Reinforcement | 23.2937 |  | MT | 0
TOTAL AMOUNT | [5 empty] | 0
3 |  | Haunch & Outer & Inner Walls
A |  | Outer, Inner walls & Haunch of Box type MNB Providing and laying in situ M35 controlled cement concrete of trap/ granite/ quartzite/ gneiss metal for RCC work in Box/solid/ deck slab etc. including ramming, vibrating, curing, formwork, centering and finishing in cement plaster excluding reinforcement etc. complete.
i |  | Side Wall Box Culvert | 45.6 |  | Cum | 0
ii |  | Haunch | 2.565 |  | Cum | 0
iii |  | Inner Walls | 89.28 |  | Cum | 0
iv |  | Reinforcement work | 15.1189 |  | MT | 0
TOTAL AMOUNT | [5 empty] | 0
4 |  | Top Slab
|  | Top Slab of Box type MNB Providing and laying in situ M35 controlled cement concrete of trap/ granite/ quartzite/ gneiss metal for RCC work in Box/solid/ deck slab etc. including ramming, vibrating, curing, formwork, centering and finishing in cement plaster excluding reinforcement etc. complete. | [5 empty] | 40.38
|  | Top Slab Box Culvert | 192.51 |  |  | 0
|  | Reinforcement | 21.1761 |  | MT | 0
TOTAL AMOUNT | [5 empty] | 0
5 |  | Rebaring work with Dowel bar
|  | Rebaring Work Providing and fixing in position TMT - FE - 500/500D bar reinforcement of various diameters for R.C.C. pile caps, footings, foundations, slabs, beams columns, canopies, staircase, newels, chajjas, lintels pardis, copings, fins, arches etc. as per detailed designs, drawings and schedules. including cutting, bending, hooking the bars, binding with wires or tack welding and supporting as required complete. - Re baring a) For TMT Fe 415 steel bars ( If Mild Steel/HYSD steel is to be used prior permission from S.E. should be taken ) | 1.1062 |  | MT | 0
TOTAL AMOUNT | [5 empty] | 0
6 |  | Miscellenous work
|  | Providing 100mm diameter GI water spouts as per detailed drawings in RCC slab and wearing surface / kerb etc. complete. | 0 |  | No | 0
|  | Providing and laying of PCC in M15 grade approach slab | 9.5475 |  | Cum | 0
|  | Providing and laying of RCC in M30 grade approach slab including reinforcement and formwork complete with fully automatic micro processor PLC with SCADA enabled reversible drum type mixer as per drawings and technical specifications etc. complete. | 19.95 |  | Cum | 0
|  | Providing Reinforced cement concrete crash barrier at the edges of the road, approaches to bridge structures and medians, constructed with R.C.C. M 40 Grade concrete with HYSD reinforcement conforming to IRC:21 and dowel bars 25 mm dia, 450 mm long at expansion joints filled with pre-moulded asphalt filler board, keyed to the structure on which it is built and installed as per design given in the enclosure to MOST circular No. RW/NH - 33022/1/94-DO III dated 24 June 1994 as per dimensions in the approved drawing and at locations directed by the Engineer, all as specified etc. complete. Spec: MORT & H 2013 Cl 811 Page No 360 | 48.4 |  | RMT | 0
|  | Providing weep holes in brick masonry /plain /reinforced concrete abutment, wing wall / return wall with 100mm diameter AC pipe extending through the full width of the structure with slope of 1V: 20H towards drawing face as per drawings and technical specifications etc. complete. | 182 |  | Nos | 0
|  | Providing tar paper bearing including laying in proper position etc. complete. | 9.6 |  | Sqm | 0
|  | Back filling behind abutment, wing wall and return wall as per drawings and technical specifications etc. complete. (by granular material) | 389.025 |  | Cum | 0
|  | Providing and laying of filter media with granular materials/ stone crushed aggregates satisfying the requirements laid down in clause 2504.2.2 of MoRTH specifications to a thickness of not less than 600 mm with smaller size towards the soil and bigger size towards the wall and provided over the entire surface behind abutment, wing wall and return wall to the full height compacted to a firm condition as per drawing and technical specifications etc. complete. | 66.69 |  | Cum | 0
|  | Flexible Apron of PCC M-15 Providing and laying in situ/ready mix/ready mix M15 cement concr ete | 161.46 |  | Cum | 0
|  | Providing and applying plastic emulsion paint of approved quality, colour and shade to new surface in three coats including scaffolding, preparing the surface. (excluding primer coat) etc. complete. | 37.884 |  | Sqm | 0
|  | Wearing coat 75 mm BC | 450.12 |  | Sqm | 0
|  | Cast in Situ Cement Concrete M20 kerb | 60 |  | Rmt | 0
|  | Painting Two Coats on New Concrete Surfaces - kerb | 20.7 |  | Rmt | 0
|  | Painting Two Coats on New Concrete Surfaces | 61.71 |  | Rmt | 0
|  | Road Marking - (Painting) | 37.884 |  | Sqm | 0
|  | Road Studs (Solar) | 25 |  | Nos | 0
0
TOTAL AMOUNT | [5 empty] | 0
TOTAL COST (Rs. In Cr) | [5 empty] | 0
[5 empty] | Per Sqm | 0
S NO. | Stones | Stone | Qty | Rate | Unit | Amount
1 | 5th km stone | 5th KM Stone | 10 |  |  | 0
2 | Km stone | Km Stone | 36 |  |  | 0
TOTAL AMOUNT | [5 empty] | 0
Note: Material & Testing shall be done as per NHAI/MORTH specification
* The Quantities mentioned in BoQ may vary up to ± 25% of original BoQ quantity of single BoQ item subject to maximum of ± 20% of original Contract price. The decision of the Employer shall be final and binding on the contractor

## Rate summary (2) (hidden)
S. No. | Items | Rates | Unit
1 | Prestressed / Reinforced cement concrete grade M-20 & above grade (Mechanical Means) | 1550.7 | Cum
2 | Dismantling of Flexible Pavements - Bituminous coarse | 629.1 | Cum
3 | Dismantling Kerb Stone | 32.9 | Rmt
4 | Dismantling of CC Crash Barrier | 1550.7 | Cum
5 | Excavation for foundation by mechanical means | 437 | Cum
6 | Excavation for foundation by mechanical means in hard murum | 437 | Cum
7 | Back filling behind abutment (by granular material) | 2320 | Cum
8 | Providing and laying of filter media with granular materials/ stone crushed aggregates | 1791 | Cum
9 | Providing and laying in situ/ready mix/ready mix M15 cement concr ete | 7006 | Cum
10 | Providing and laying in situ M35 controlled cement concrete | 8578 | Cum
11 | Providing and fixing in position TMT - FE - 500/500D bar reinforcement - Dowel bar | 74872 | MT
12 | Providing and fixing in position TMT - FE - 500/500D bar reinforcement Mild Steel/HYSD steel is to be used prior permission from S.E. should be taken ) | 84370.37 | MT
13 | 100mm diameter GI water spouts | 3848 | No
14 | RCC in M30 grade approach slab | 6624 | Cum
15 | Reinforced cement concrete crash barrier | 4391 | RMT
16 | Weep holes in brick masonry /plain /reinforced concrete abutment, wing wall / return wall with 100mm | 635 | Nos
17 | Tar paper bearing including laying in proper position etc. complete. | 90 | Sqm
18 | Emulsion paint | 1280.0172 | Sqm
19 | Wearing coat 75 mm BC | 1681.82 | Sqm
20 | Cast in Situ Cement Concrete M20 kerb | 298 | Rmt
21 | Painting Two Coats on New Concrete Surfaces | 136 | Rmt
22 | Road Marking - (Painting) | 431 | Sqm
23 | Road Studs (Solar) | 267 | Nos

## Measurement - MNB (2)
Name of work
TOLLING, OPERATION, MAINTENANCE & TRANSFER OF SIX LANE WITH PAVED SHOULDER OF GUNDUGOLANU - CHINNA AVUTAPALLI SECTION FROM EXISTING KM 1023+496 TO 1076+280 OF NH-16 IN THE STATE OF ANDHRA PRADESH
Sub Estimate No. 7 : Minor Bridge work
Measurement Sheet (CH : 1067+320)
BoQ Item No. | Description of Items | No. | Length | Breadth | Depth | Quantity | Unit | Observation | Compliance
Dismanlting of Existing Bridge
1 | Dismantling of Structures (Dismantling of existing structures like culverts, bridges, retaining walls and other structure comprising of masonry, cement concrete, wood work, steel work, including T&P and scaffolding wherever necessary, sorting the dismantled material, disposal of unserviceable material and stacking the serviceable material with all lifts and lead of 1000 metres)
a | Prestressed / Reinforced cement concrete grade M-20 & above | 1 |  |  |  | 541.716 | Cum |  | -
b | Dismantling of Flexible Pavements (Dismantling of flexible pavements and disposal of dismantled materials up to a lead of 1000 metres, stacking serviceable and unserviceable materials separately) - machanically
c | Bituminous Coarse | 1 | 48.34 | 9.3 | 0.075 | 33.7171 | Cum |  | -
d | Dismantling Kerb Stone (Dismantling kerb stone by manual means and disposal of dismantled material with all lifts and up to a lead of 1000 metre) | 1 | 60 |  |  | 60 | Rmt |  | -
e | Dismantling of CC Crash Barrier | 1 | 41.4 | 0.26325 |  | 10.8986 | Cum |  | -
2 | Excavation for foundation by mechanical means in earth, soils of all types, sand, gravel, soft murum including shoring and strutting as necessary and disposing off excavated stuff as directed etc. complete.
| Box Structure | 1 | 41.4 | 9.3 | 1.25 | 481.275 | Cum |  | -
[5 empty] | Total | 481.275
a | Quantity for this item @ 60% | 60% | 481.275 |  |  | 288.765 | Cum |  | -
3 | Excavation for foundation by mechanical means in hard murum including shoring and strutting as necessary and disposing off excavated stuff as directed etc. complete.
a | Quantity for this item @ 40% | 40% | 481.275 |  |  | 192.51 | Cum | Quantity for this item assumed as 25% but calculated based on 40%. Pls. clarify | Quantity will be considered on the safe side.
4 | Excavation for foundation by mechanical means in soft rock including shoring and strutting as necessary and disposing off excavated stuff as directed etc. complete.
a | Quantity for this item @ 13% | 0% | 481.275 |  |  | 0 | Cum
5 | Excavation for foundation in hard rock by controlled blasting including shoring and strutting as necessary and disposing off excavated stuff as directed etc. complete.
a | Quantity for this item @ 1% | 0% | 481.275 |  |  | 0 | Cum
6 | Excavation for foundation in hard rock by chiselling and wedging or line drilling including shoring and strutting as necessary and disposing off excavated stuff as directed etc. complete. (excluding dewatering)
a | Quantity for this item @ 1% | 0% | 481.275 |  |  | 0 | Cum
7 | Back filling behind abutment, wing wall and return wall as per drawings and technical specifications etc. complete. (by granular material)
a | Behind Wall | 2 | 9.5 | 3.5 | 5.85 | 389.025 | Cum
8 | Providing and laying of filter media with granular materials/ stone crushed aggregates satisfying the requirements laid down in clause 2504.2.2 of MoRTH specifications to a thickness of not less than 600 mm with smaller size towards the soil and bigger size towards the wall and provided over the entire surface behind abutment, wing wall and return wall to the full height compacted to a firm condition as per drawing and technical specifications etc. complete.
a | On side of Box | 2 | 9.5 | 0.6 | 5.85 | 66.69 | Cum
[5 empty] | Total | 66.69 | Cum
9 | Pr oviding and laying in situ / r eady mix / r eady mix M15 cement concr ete of tr ap/ gr anite/ quar tzite/ gneiss metal in foundation including necessar y center ing, for mw or k, bailing out w ater , compacting and cur ing etc. complete. (w ith fully automatic micr o pr ocessor based PLC w ith SCADA enabled w ith r ever sible dr um type mixer / concr ete batch mix plant (pan mixer ) w ith natur al / ar tifical sand)
a | Box MNB | 1 | 9.3 | 41.4 | 0.1 | 38.502 | Cum | It is MNB, not Box Culvert | Noted. It is a Box Type Minor Bridge
b | Shear Key | 2 |  |  |  | 0.744 | Cum
c | Apron | 2 |  |  |  | 161.46 | Cum
d | Flat stone apron | 2 |  |  |  | 322.92 | Cum
[5 empty] | Total | 39.246 | Cum
10 | Providing and laying in situ M35 controlled cement concrete of trap/ granite/ quartzite/ gneiss metal for RCC work in solid/ deck slab etc. including ramming, vibrating, curing, formwork, centering and finishing in cement plaster excluding reinforcement etc. complete. (height up to 3 meter with fully automatic micro processor based PLC with SCADA enabled reversible drum type mixer and natural sand)
a | Top Slab Box Culvert | 1 | 9.3 | 41.4 | 0.5 | 192.51 | Cum | It is MNB, not of Box Culvert | Noted. It is a Box Type Minor Bridge
b | Base Raft Box Culvert | 1 | 9.3 | 41.4 | 0.55 | 211.761 | Cum
c | Side Wall Box Culvert | 2 | 9.5 | 0.5 | 4.8 | 45.6 | Cum | Verify height of wall. Average height should be considered as (4.744+4.218)/2 =4.481 | Quantity will be considered on the safe side.
d | Haunch | 24 | 9.5 | 0.01125 |  | 2.565 | Cum | Verify Sectional area of each Haunch (0.045). Corrected area should be 1/2x(0.15x.15)= 0.01125 | Quantity will be considered on the safe side.
e | Inner Walls | 5 | 9.3 | 0.4 | 4.8 | 89.28 | Cum | Verify height of wall. Average height should be considered as (4.744+4.218)/2 =4.481 | Quantity will be considered on the safe side.
[5 empty] | Total | 541.716 | Cum
11 | Providing and fixing in position TMT - FE - 500 bar reinforcement of various diameters for R.C.C. pile caps, footings, foundations, slabs, beams columns, canopies, staircase, newels, chajjas, lintels pardis, copings, fins, arches etc. as per detailed designs, drawings and schedules. including cutting, bending, hooking the bars, binding with wires or tack welding and supporting as required complete. a) For TMT Fe 415 steel bars ( If Mild Steel/HYSD steel is to be used prior permission from S.E. should be taken )
| Total RCC Concrete |  |  |  |  | 541.716 | Cum
a | Steel @ 110 kg/cum |  | 541.716 | X | 110 | 59.5888 | MT | Steel assumed @ 110 kg/Cum. But calculated based on 73.5 Kg/Cum. Pls clarify. It is better to calculate Steel quantity based on BBS as Reinforcement drawing is already there. | Noted and after checking the BBS will finalize the quantity of Steel.
b | 20 mm Dowel bar @ 300 mm C/C (Reinforced Lap) |  |  |  |  | 1.1062 | MT
12 | Providing 100mm diameter GI water spouts as per detailed drawings in RCC slab and wearing surface / kerb etc. complete. | 1 | 6 |  |  | 3 | No.
13 | Providing and laying of RCC in M30 grade approach slab including reinforcement and formwork complete with fully automatic micro processor PLC with SCADA enabled reversible drum type mixer as per drawings and technical specifications etc. complete. | 2 | 3.5 | 9.5 | 0.3 | 19.95 | Cum
14 | Providing & laying of PCC in M15 grade Approch slab | 2 | 3.35 | 9.5 | 0.15 | 9.5475 | Cum
15 | Providing Reinforced cement concrete crash barrier at the edges of the road, approaches to bridge structures and medians, constructed with R.C.C. M 40 Grade concrete with HYSD reinforcement conforming to IRC:21 and dowel bars 25 mm dia, 450 mm long at expansion joints filled with pre-moulded asphalt filler board, keyed to the structure on which it is built and installed as per design given in the enclosure to MOST circular No. RW/NH - 33022/1/94-DO III dated 24 June 1994 as per dimensions in the approved drawing and at locations directed by the Engineer, all as specified etc. complete. Spec: MORT & H 2013 Cl 811 Page No 360 | 1 | 48.4 |  |  | 48.4 | RMT | 1. generally Crash Barrier continues on Approach Slab i.e. length should be (41.4+3.5x2)= 48.4). Pls check and confirm. 2.Grade of concrete for RCC Crash Barrier commonly used as M-40. Please once reconfirm whether M25 concrete or M40 to be provided. | Noted and Corrected accordingly.
17 | Providing weep holes in brick masonry /plain /reinforced concrete abutment, wing wall / return wall with 100mm diameter AC pipe extending through the full width of the structure with slope of 1V: 20H towards drawing face as per drawings and technical specifications etc. complete.
No. of holes 2 per 1 sqm
| Box Walls | 2 | 9.5 |  | 4.8 | 91.2 | Sqm
| No. of holes |  | 91.2 | X | 2 | 182 | Nos
a | Weep Holes |  |  |  | Total | 91.2 | Sqm
18 | Providing tar paper bearing including laying in proper position etc. complete. | 4 | 4.8 | 0.5 |  | 9.6 | SQM
19 | Pr oviding and applying plastic emulsion paint of appr oved quality, colour and shade to new sur face in thr ee coats including scaffolding, pr epar ing the sur face. (excluding pr imer coat) etc. complete. | 2 | 55.4 |  |  | 37.884 | Sqm
20 | Cast in Situ Cement Concrete M20 kerb |  |  |  |  | 60 | Rmt
21 | Painting Two Coats on New Concrete Surfaces - kerb |  |  |  |  | 20.7 | Sqm
| Painting Two Coats on New Concrete Surfaces - CC Barrier |  |  |  |  | 61.71 | Sqm
22 | Providing and laying M15 concrete for Apron embedment as per the existing bridge condition at site | 2 |  |  |  | 161.46 | Cum | Further, if possible please add some quantities for Quarter Coning & Flexible Apron of existing bridge as the photographs indicates that condition of Stone Pitching & Apron may not be proper. | Noted and shall be considered.