## Summary
Tender No. NEPPL/FY25-26/RFP/Kochugaon, Assam/RCC Crash Barrier
Tender Name:Request for Proposal (“RFP”) issued by NHIT Eastern Projects Private Limited (NEPPL) for Engagement of Agency/Firm for Crash barrier works at four-lane of Kochugaon - Khaljhar (WB / Assam Border - Bijni – Manikpur) road Section of NH-27 (project length - 114.171 kms) in the state of Assam.
| S.No | Item Description | Short Description | Unit | Quantity | Rate | Total Amount
| 1 | Dismantling of Existing Concrete Structures Dismantling of existing concrete structures including breaking and removal of concrete, cutting and removal of embedded reinforcement, clearing the site, and transportation and disposal of debris to an approved disposal site, all as directed by the Engineer-in-Charge. The work shall be executed using appropriate equipment and necessary safety measures to prevent any damage to adjoining structures. The activity shall be carried out strictly in accordance with the methodology provided in the approved Scope document and relevant specifications. The quoted rate shall include all costs necessary to complete the work in accordance with the specifications, drawings, and directions of the Engineer-in-Charge, including but not limited to the cost of all labour, materials, machinery, tools, plants, transportation, handling, testing, safety arrangements, temporary works, site clearance, and lead charges for transportation and disposal of dismantled material up to a distance of 10 km from the site location, whether specifically mentioned or implied. | Dismantling of Existing Concrete Structures | RMT | 4707.7 |  | 0
| 2 | Application of Emulsion Paint / Enamel Paint on Concrete Handrails / Crash Barrier Providing and applying two coats of approved quality exterior-grade emulsion paint or synthetic enamel paint, as specified, on unplastered concrete surfaces of handrails / crash barrier after thorough surface preparation. Surface preparation shall be carried out in accordance with relevant provisions of IS 2395 (Part 1): 1994 and manufacturer’s recommendations. The surface shall be cleaned of all dirt, dust, grease, oil, efflorescence, algae, moss, and loose particles by wire brushing, scraping, and water jetting, followed by complete drying. A suitable cement-based or acrylic primer compatible with the paint system shall be applied to ensure proper adhesion on concrete surfaces prior to painting, as per manufacturer’s specifications. The paint shall be applied at the recommended coverage rate specified by the manufacturer, ensuring uniform thickness, colour, shade, and finish. Painting shall be carried out using appropriate tools such as brushes, rollers, or spray equipment in two coats, with adequate drying time between coats as per manufacturer’s instructions and relevant IS standards. The quoted rate shall include all costs necessary to complete the work in accordance with the specifications, drawings, and directions of the Engineer-in-Charge, including but not limited to the cost of all labour, materials, primers, paints, machinery, tools, plants, transportation, handling, testing, safety arrangements, temporary works, and site clearance, whether specifically mentioned or implied. | Application of Paint on Concrete Handrails / Crash Barrier | RMT | 4707.7 |  | 0
| 3 | Reconstruction of RCC Crash Barrier (Post Dismantling) : (1) Construction of new RCC crash barrier in place of a damaged or dismantled barrier, including preparation of base surface, layout marking, supplying and fixing steel reinforcement conforming to IS:1786, fixing dowel bars / anchor rebars (wherever required) by core drilling and grouting with approved resin-based compound, providing and fixing steel formwork, and placing M40 grade concrete using mechanical or manual methods. (2) The concrete shall be produced using Ordinary Portland Cement (OPC) 53 Grade conforming to IS 12269, sourced only from NHI / NHIT approved manufacturers as per the latest approved vendor list. Aggregates shall conform to IS 383 and water shall be potable and conform to IS 456 requirements. Concrete mix design shall be approved by the Engineer-in-Charge prior to execution. (3) The scope includes proper compaction by needle vibrators, finishing, curing for a minimum period of 7 days (or as specified by MoRTH / IRC), de-shuttering, surface rectification, and making good of joints, all in line with approved drawings, MoRTH Specifications, and site requirements. This work shall be carried out in accordance with MoRTH Specifications: Section 1700 – Concrete Section 1500 – Formwork Section 1600 – Reinforcement Section 2703 – Crash Barrier (dimensions, geometry, and safety requirements) (1) The contractor shall ensure proper jointing with existing structures, continuity of reinforcement, and correct alignment to achieve the required safety performance of the crash barrier. (II) The quoted rate shall include the cost of all materials (including OPC 53 Grade cement from approved sources), labour, formwork, reinforcement, dowel fixing, resin grouting, equipment, machinery, tools, safety barriers, curing arrangements, testing, site cleaning, and all incidental works. No extra payment shall be made for dowel fixing, formwork over uneven bases, working in restricted locations, or any other associated activity. (III) The finished crash barrier shall be true to line, level, and plumb, with uniform cross-section, proper cover, and a sound, smooth surface finish, as approved by the Engineer-in-Charge. | Reconstruction of RCC Crash Barrier (Post Dismantling) | RMT | 4707.7 |  | 0
[5 empty] | Total |  | 0
[5 empty] | GST 18 % |  | 0
[5 empty] | Total Amount |  | 0
Note: Material & Testing shall be done as per NHAI/MORTH specification
* The Quantities mentioned in BoQ may vary up to ± 25% of original BoQ quantity of single BoQ item subject to maximum of ± 20% of original Contract price. The decision of the Employer shall be final and binding on the contractor

## FY 26-27
Tender No. NEPPL/FY25-26/RFP/Kochugaon, Assam/RCC Crash Barrier
Tender Name:Request for Proposal (“RFP”) issued by NHIT Eastern Projects Private Limited (NEPPL) for Engagement of Agency/Firm for Crash barrier works at four-lane of Kochugaon - Khaljhar (WB / Assam Border - Bijni – Manikpur) road Section of NH-27 (project length - 114.171 kms) in the state of Assam.
SI.NO | Chainage | Side | Type of Structure | Length as per Sch B | Length Additional for Approach Slab | Total Length | Remarks
1 | 46+914 | RHS | MJB | 404 | 14 | 418 | Low Height - Need to Change
2 | 53+594 | LHS | MNB | 53 | 14 | 67 | Hand Rail - Good Condition
| 53+594 | RHS | MNB | 53 | 14 | 67 | Low Height - Need to Change
3 | 55+302 | LHS | MNB | 55 | 14 | 69 | Hand Rail - Good Condition
| 55+302 | RHS | MNB | 55 | 14 | 69 | Hand Rail - Good Condition
4 | 60+210 | LHS | MNB | 40.8 | 14 | 54.8 | Hand Rail - Good Condition
| 60+210 | RHS | MNB | 40.8 | 14 | 54.8 | Hand Rail - Good Condition
5 | 67+880 | LHS | MNB | 42 | 14 | 56 | Hand Rail - Good Condition
| 67+880 | RHS | MNB | 42 | 14 | 56 | Hand Rail - Good Condition
6 | 68+350 | LHS | MNB | 21 | 14 | 35 | Hand Rail - Good Condition
| 68+350 | RHS | MNB | 21 | 14 | 35 | Hand Rail - Good Condition
7 | 69+720 | LHS | MNB | 21 | 14 | 35 | Hand Rail - Good Condition
| 69+720 | RHS | MNB | 21 | 14 | 35 | Hand Rail - Good Condition
8 | 70+170 | LHS | MNB | 81.6 | 14 | 95.6 | Hand Rail - Good Condition
| 70+170 | RHS | MNB | 81.6 | 14 | 95.6 | Hand Rail - Good Condition
9 | 70+380 | LHS | MNB | 54 | 14 | 68 | Hand Rail - Good Condition
| 70+380 | RHS | MNB | 54 | 14 | 68 | Hand Rail - Good Condition
10 | 71+340 | LHS | MNB | 29 | 14 | 43 | Hand Rail - Good Condition
| 71+340 | RHS | MNB | 29 | 14 | 43 | Hand Rail - Good Condition
11 | 72+230 | LHS | MNB | 106 | 14 | 120 | Hand Rail - Good Condition
| 72+230 | RHS | MNB | 106 | 14 | 120 | Hand Rail - Good Condition
12 | 72+570 | LHS | MNB | 29 | 14 | 43 | Hand Rail - Good Condition
| 72+570 | RHS | MNB | 29 | 14 | 43 | Hand Rail - Good Condition
13 | 73+310 | LHS | MNB | 21 | 14 | 35 | Hand Rail - Good Condition
| 73+310 | RHS | MNB | 21 | 14 | 35 | Hand Rail - Good Condition
14 | 74+380 | LHS | MNB | 42 | 14 | 56 | Hand Rail - Good Condition
| 74+380 | RHS | MNB | 42 | 14 | 56 | Hand Rail - Good Condition
15 | 74+800 | LHS | MNB | 78.8 | 14 | 92.8 | Hand Rail - Good Condition
| 74+800 | RHS | MNB | 78.8 | 14 | 92.8 | Hand Rail - Good Condition
16 | 75+885 | LHS | MNB | 21 | 14 | 35 | Hand Rail - Good Condition
| 75+885 | RHS | MNB | 21 | 14 | 35 | Hand Rail - Good Condition
17 | 76+060 | BHS | MNB | 157.6 | 28 | 185.6 | Hand Rail - Good Condition
18 | 77+010 | BHS | MNB | 40 | 28 | 68 | Hand Rail - Good Condition
19 | 77+560 | BHS | MNB | 54 | 28 | 82 | Hand Rail - Good Condition
20 | 78+760 | LHS | MNB | 41 | 14 | 55 | Hand Rail - Good Condition
| 78+760 | RHS | MNB | 41 | 14 | 55 | Hand Rail - Good Condition
21 | 80+940 | LHS | MNB | 19.8 | 14 | 33.8 | Hand Rail - Good Condition
| 80+940 | RHS | MNB | 19.8 | 14 | 33.8 | Hand Rail - Good Condition
22 | 83+190 | LHS | MNB | 19.8 | 14 | 33.8 | Hand Rail - Good Condition
| 83+190 | RHS | MNB | 19.8 | 14 | 33.8 | Hand Rail - Good Condition
23 | 963+867 | LHS | MJB | 665.7 | 14 | 679.7 | Low Height - Need to Change
24 | 970+531 | BHS | MNB | 37.6 | 28 | 65.6 | Hand Rail - Good Condition
25 | 974+411 | BHS | MNB | 29.6 | 28 | 57.6 | Hand Rail - Good Condition
26 | 975+234 | BHS | MJB | 414.7 | 14 | 428.7 | Hand Rail - Good Condition
27 | 980+012 | RHS | MNB | 18 | 14 | 32 | Hand Rail - Good Condition
28 | 983+620 | LHS | MNB | 24.4 | 14 | 38.4 | Hand Rail - Fair Condition
29 | 996+117 | LHS | MJB | 391.5 | 14 | 405.5 | Hand Rail - Fair Condition
30 | 1006+155 | LHS | MNB | 36 | 14 | 50 | Hand Rail In good Condition
31 | 1007+252 | LHS | MNB | 30 | 14 | 44 | Hand Rail In good Condition
32 | 1012+588 | RHS | MNB | 83 | 14 | 97 | Hand Rail In good Condition
|  |  |  | 3937.7 | 770 | 4707.7
|  |  |  | Total |  | 4707.7

## FY 25-26 (hidden)
No. Bridge | Chainage | Side | Type of Structure | Length as per Sch B | Length Additional for Approach Slab | Total Length | As per Schedule B | Remarks | Pripority | Remarks
1 | 30+327 | LHS | MNB | 54 | 14 | 68 | Provide New Crash Barrier | Considering Schedule B | P4 | Hand Rail - Good Condition
| 30+327 | RHS | MNB | 54 | 14 | 68 | Provide New Crash Barrier | Considering Schedule B | P1 | Accident Happen- Low Height
2 | 32+335 | LHS | MNB | 53 | 14 | 67 | Provide New Crash Barrier | Considering Schedule B | P3 | Low Height - Need to Change
| 32+335 | RHS | MNB | 53 | 14 | 67 | Provide New Crash Barrier | Considering Schedule B | P4 | Hand Rail - Good Condition
3 | 34+089 | RHS | MJB | 313 | 14 | 327 | Provide New Crash Barrier | Considering Schedule B | P3 | Low Height - Need to Change
4 | 39+693 | LHS | MNB | 54 | 14 | 68 | Provide New Crash Barrier | Considering Schedule B | P3 | Low Height - Need to Change
| 39+693 | RHS | MNB | 54 | 14 | 68 | Provide New Crash Barrier | Considering Schedule B | P4 | Hand Rail - Good Condition
5 | 40+160 | BHS | PUP | 14 | 14 | 28 | Provide New Crash Barrier | Considering Schedule B | P4 | Hand Rail - Good Condition
6 | 41+300 | BHS | MNB | 20 | 14 | 34 | Provide New Crash Barrier | Considering Schedule B | P4 | Hand Rail - Good Condition
7 | 42+057 | LHS | MNB | 30 | 14 | 44 | Provide New Crash Barrier | Considering Schedule B | P2 | Damage - Low Height
| 42+057 | RHS | MNB | 20 | 14 | 34 | Provide New Crash Barrier | Considering Schedule B | P4 | Hand Rail - Good Condition
8 | 44+201 | LHS | MNB | 54 | 14 | 68 | Provide New Crash Barrier | Considering Schedule B | P4 | Hand Rail - Good Condition
| 44+201 | RHS | MNB | 54 | 14 | 68 | Provide New Crash Barrier | Considering Schedule B | P2 | Low Height - Need to Change
9 | 45+150 | RHS | MJB | 175.5 | 14 | 189.5 | Provide New Crash Barrier | Considering Schedule B | P1 | Accident Happen- Low Height | 189.5
10 | 45+532 | RHS | MJB | 177 | 14 | 191 | Provide New Crash Barrier | Considering Schedule B | P2 | Damage - Low Height | 191
11 | 48+231 | LHS | MNB | 29 | 14 | 43 | Provide New Crash Barrier | Considering Schedule B | P2 | Damage - Low Height
| 48+231 | RHS | MNB | 29 | 14 | 43 | Provide New Crash Barrier | Considering Schedule B | P4 | Hand Rail - Good Condition
12 | 48+696 | LHS | MNB | 29 | 14 | 43 | Provide New Crash Barrier | Considering Schedule B | P2 | Low Height - Need to Change
| 48+696 | RHS | MNB | 29 | 14 | 43 | Provide New Crash Barrier | Considering Schedule B | P4 | Hand Rail - Good Condition
13 | 49+096 | LHS | MNB | 42 | 14 | 56 | Provide New Crash Barrier | Considering Schedule B | P1 | Accident Happen
| 49+096 | RHS | MNB | 42 | 14 | 56 | Provide New Crash Barrier | Considering Schedule B | P1 | Accident Happen
14 | 50+681 | LHS | MNB | 21.7 | 14 | 35.7 | Provide New Crash Barrier | Considering Schedule B | P2 | Damage - Low Height
| 50+681 | RHS | MNB | 21.7 | 14 | 35.7 | Provide New Crash Barrier | Considering Schedule B | P4 | Hand Rail - Good Condition
15 | 50+870 | LHS | MNB | 29 | 14 | 43 | Provide New Crash Barrier | Considering Schedule B | P2 | Damage - Low Height
| 50+870 | RHS | MNB | 29 | 14 | 43 | Provide New Crash Barrier | Considering Schedule B | P4 | Hand Rail - Good Condition
16 | 52+229 | LHS | MNB | 60 | 14 | 74 | Provide New Crash Barrier | Considering Schedule B | P4 | Hand Rail - Good Condition
| 52+229 | RHS | MNB | 60 | 14 | 74 | Provide New Crash Barrier | Considering Schedule B | P2 | Damage - Low Height
17 | 57.152 | LHS | MJB | 82 | 14 | 96 | Provide New Crash Barrier | Considering Schedule B | P2 | Damage - Low Height
| 57.152 | RHS | MJB | 82 | 14 | 96 | Provide New Crash Barrier | Considering Schedule B | P4 | Hand Rail - Good Condition
18 | 58.85 | LHS | MNB | 106 | 14 | 120 | Provide New Crash Barrier | Considering Schedule B | P4 | Hand Rail - Good Condition
| 58.85 | RHS | MNB | 106 | 14 | 120 | Provide New Crash Barrier | Considering Schedule B | P2 | Damage - Low Height
19 | 60+420 | LHS | MNB | 46 | 14 | 60 | Provide New Crash Barrier | Considering Schedule B | P4 | Hand Rail - Good Condition
| 60+420 | RHS | MNB | 46 | 14 | 60 | Provide New Crash Barrier | Considering Schedule B | P2 | Damage - Low Height
20 | 60+610 | LHS | MNB | 19.8 | 14 | 33.8 | Provide New Crash Barrier | Considering Schedule B | P2 | Damage - Low Height
| 60+610 | RHS | MNB | 19.8 | 14 | 33.8 | Provide New Crash Barrier | Considering Schedule B | P2 | Damage - Low Height
21 | 62.83 | LHS | MJB | 349.6 | 14 | 363.6 | Provide New Crash Barrier | Considering Schedule B | P1 | Accident
22 | 66+510 | LHS | MNB | 40.8 | 14 | 54.8 | Provide New Crash Barrier | Considering Schedule B | P4 | Hand Rail - Good Condition
| 66+510 | RHS | MNB | 41 | 14 | 55 | Provide New Crash Barrier | Considering Schedule B | P2 | Damage - Low Height
23 | 68+690 | BHS | MNB | 81.8 | 14 | 95.8 | Provide New Crash Barrier | Considering Schedule B | P1 | Accident
24 | 69+460 | LHS | MNB | 40.8 | 14 | 54.8 | Provide New Crash Barrier | Considering Schedule B | P4 | Hand Rail - Good Condition
| 69+460 | RHS | MNB | 40.8 | 14 | 54.8 | Provide New Crash Barrier | Considering Schedule B | P2 | Damage - Low Height
25 | 73+840 | LHS | MNB | 29 | 14 | 43 | Provide New Crash Barrier | Considering Schedule B | P2 | Damage - Low Height
| 73+840 | RHS | MNB | 29 | 14 | 43 | Provide New Crash Barrier | Considering Schedule B | P2 | Damage - Low Height
26 | 75+160 | LHS | MNB | 53 | 14 | 67 | Provide New Crash Barrier | Considering Schedule B | P4 | Hand Rail - Good Condition
| 75+160 | RHS | MNB | 53 | 14 | 67 | Provide New Crash Barrier | Considering Schedule B | P2 | Damage - Low Height
27 | 86+415 | LHS | MNB | 103.6 | 14 | 117.6 | Provide New Crash Barrier | Considering Schedule B | P2 | Damage - Low Height
| 86+415 | RHS | MNB | 103.6 | 14 | 117.6 | Provide New Crash Barrier | Considering Schedule B | P4 | Hand Rail - Good Condition
28 | 962+934 | LHS | MNB | 29 | 14 | 43 | Provide New Crash Barrier | Considering Schedule B | P1 | Accident
29 | 980+012 | LHS | MNB | 18 | 14 | 32 | Provide New Crash Barrier | Considering Schedule B | P1 | Accident
30 | 984+350 | LHS | MNB | 24.9 | 14 | 38.9 | Provide New Crash Barrier | Considering Schedule B | P1 | Accident
31 | 986+294 | LHS | MJB | 414 | 14 | 428 | Provide New Crash Barrier | Considering Schedule B | P2 | Damage - Low Height
32 | 1010+466 | LHS | MNB | 28 | 14 | 42 | Provide New Crash Barrier | Considering Schedule B | P1 | Accident
|  |  | Total Length |  |  | 4316.4
|  |  | As per WO quantity |  |  | 4316
|  |  | 6 | 36+635 | BC | 1X3.0 | BHS
|  |  | 4 | 35+340 | BC | 1X4.0 | BHS
|  |  | 3 | 34+860 | BC | 1X3.5 | BHS
|  |  | 1 | 33+165 | Slab Culvert | 1X3.0 | BHS
|  |  | 6 | 36+635 | BC | 1X3.0 | BHS
|  |  | 10 | 39+303 | BC | 1X2.50